## Overview
LittleStory AI — Jira Board & Delivery Workbook
Little Stories. Big Imagination. · Generated 29 Oct 2026 from the master orchestrator prompt and the Figma Make design pack
Project | LittleStory AI – child-friendly AI storytelling app (ages 3–12) with parent controls
Objective | Production-quality, maintainable, accessible, multilingual native Android app that faithfully implements the approved Figma design, with no hardcoded values.
Platform | Native Android · Kotlin · Jetpack Compose · Material 3 (customised)
Languages | MVP: English (default & fallback) and Kannada (ಕನ್ನಡ). Future languages added via resources + registry only (no feature-code change).
Design source | https://www.figma.com/make/2DYtUW39GtnsDpUd5jSu6x/Mobile-App-UI-Prototype?p=f&t=7bdm57yPvNI3NZ8f-0
Design pack | docs/design/ – 22 screenshots (18 screens), design-tokens.json, LittleStory_Figma_Design_Details.md (see 'Screens' and 'Design Gallery' sheets)
Repository | https://github.com/shivayogih/LittleStory
Dev environment | Windows + macOS · Android Studio · Claude Code CLI · GitHub · GitHub Copilot
MVP scope | 18 designed screens with deterministic local mock data in EN/KN; simulated story generation, narration, downloads and demo subscription (clearly labelled).
Out of scope (MVP) | Real AI provider, backend, auth, cloud sync, analytics, real payments, production TTS/streaming, remote notifications, runtime machine translation, languages beyond EN/KN in the shipped UI.
Architecture principles | Clean layers (UI → ViewModel → use case → repository) · immutable UiState + StateFlow · design tokens only · string resources only (UiText in VMs) · central AppConfig & feature flags · per-language mock JSON · Hilt DI · no circular module deps
No-hardcoding policy | Text → strings.xml (EN + KN) · colours/dims/type → design tokens · limits/timings/options → AppConfig · routes → typed destinations · mock data → assets/mock JSON · versions → libs.versions.toml · languages → SupportedLanguage registry
Approval rules | A Discovery (read-only) · B Documentation · C Implementation · D Push/PR · E Merge (owner only) · F Release (owner only). One approval never implies the next.
Branch strategy | main (release) ← development (integration) ← feature/LS-###-slug · fix/LS-###-slug. Every PR targets development; owner reviews and merges.
Current milestone | P1 Requirements & planning — Approval B granted 29 Oct 2026; docs, prompts, CLAUDE.md and copilot instructions drafted on claude/project-thread-veobz7, awaiting owner review. P0 discovery (LS-001, LS-002) done.
Key risks | Old 'LittleKatha' brand in designs · 7 design languages vs EN/KN · fonts lack Kannada glyphs · missing designs (splash, language prefs, privacy, help) · contrast & touch targets · Kannada reviewer availability. See 'Risks & Questions' · cloud workspace cannot build Android (R-21) · default branch misconfigured (R-22).
Progress (live)
Tickets total
Done
In progress / in review
Blocked / needs clarification
Story points total
Story points done
% points complete
How to use
Board | Kanban view – updates automatically when you change Status in 'Backlog'.
Backlog | Edit Status, Assignee, PR Link, Test Evidence, Actual Result, Kannada Translation Status (dropdowns provided). Do not rename Issue Keys.
Screens / Design Gallery | Screenshot thumbnails, full design details, links to the full screenshots in docs/design/screens/ and to Figma.
Translations | Fill the Kannada column; keep status 'Needs native review' until a fluent reviewer approves.
Legend | Editable columns have a cream header note. Grey 'Board Key' column in Backlog is a formula – do not edit.

## Board
Kanban Board
Live view of the Backlog sheet – change a ticket's Status there and it moves here. Columns list 'Key · Summary'.
| To Do | In Progress | In Review | Blocked | Done | 'Needs Clarification' tickets appear in Dashboard → By status.

## Dashboard
Dashboard
All figures are formulas over Backlog, Screens, Test Cases and Translations.
Key figures
Total tickets
Total story points
Blocked tickets
Awaiting human review (In Review)
Awaiting merge (Git-PR-CI)
Failed checks (Git-PR-CI)
Open dependencies (not Done, has deps)
Screens with design missing
Screens not yet verified
Test cases not passing
Kannada strings missing
Kannada strings awaiting native review
By status | Tickets | Points | By priority | Tickets | Points | By MoSCoW | Tickets | Points
To Do |  |  | Highest |  |  | Must
In Progress |  |  | High |  |  | Should
In Review |  |  | Medium |  |  | Could
Blocked |  |  | Low |  |  | Won't
Done
Needs Clarification
By phase | Tickets | Points | By type | Tickets | Points | By Kannada status | Tickets | Points
P0 |  |  | Story |  |  | N/A
P1 |  |  | Task |  |  | Missing
P2 |  |  | Bug |  |  | Draft
P3 | [5 empty] | Needs native review
P4 | [5 empty] | Approved
P5
P6
P7
P8
By epic | Tickets | Points
LS-EPIC-01
LS-EPIC-02
LS-EPIC-03
LS-EPIC-04
LS-EPIC-05
LS-EPIC-06
LS-EPIC-07
LS-EPIC-08
LS-EPIC-09
LS-EPIC-10
LS-EPIC-11
LS-EPIC-12
LS-EPIC-13
LS-EPIC-14
LS-EPIC-15

## Backlog
Issue Key | Issue Type | Epic Link | Summary | Description | User Story | Business Value | Priority | MoSCoW | Phase | Component/Module | Screen ID | Figma Frame Reference | Dependencies | Blocks / Blocked By | Acceptance Criteria | Definition of Done | Implementation Notes | Required Tests | Test Evidence | Estimate (Story Points) | Estimated Complexity | Risk | Agent Role | Parallelizable | Shared File Conflict Risk | Branch Name | Pull Request Link | Assignee | Status | Reviewer | Approval Status | Actual Result | Localization Impact | Kannada Translation Status | Notes | Requirement IDs | Board Key (formula)
LS-001 | Task | LS-EPIC-01 | Read-only repository & toolchain discovery | Inspect local repo, git state, branches, Gradle/AGP/Kotlin/JDK/SDK versions, modules, manifests, tests, CI, existing docs, cross-platform readiness (gradlew/gradlew.bat, .gitattributes, encodings). No file changes. | – | Delivery clarity – avoids rework | Highest | Must | P0 | Repo / tooling | – | – | None | Blocks: LS-003, LS-005, LS-007, LS-008, LS-030, LS-131 Blocked by: – | 1. Discovery report covers all 17 items of master prompt §2.2 2. Zero files changed (git status clean before/after) 3. Toolchain versions and compatibility issues listed 4. Report ends with Approval gate question | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | N/A (read-only) – verify `git status` unchanged | Read-only: git/GitHub inspection, Figma whoami, network probes | 3 | Medium | Low | Orchestrator | Yes | Low | feature/LS-001-read-only-repository-toolchain-discovery |  |  | Done | Project owner (human) | Approval A — report delivered | P0 assessment delivered 29 Oct 2026 (Claude Doc "LittleStory — P0 Discovery Assessment"): repo docs-only, default branch misconfigured, Figma Make not readable by agents, cloud workspace cannot reach dl.google.com. | None | N/A | Run on owner's machine via Claude Code CLI. | NFR-09
LS-002 | Task | LS-EPIC-01 | Extract Figma Make design: screen inventory, tokens, specs | Inventory all screens/states of Figma Make file 2DYtUW39GtnsDpUd5jSu6x; extract tokens, typography, components, motion, copy and accessibility gaps. | – | Delivery clarity – avoids rework | Highest | Must | P0 | Design | SCR-01…SCR-18 | Design pack – all screens (docs/design/screens/) | None | Blocks: LS-003, LS-004, LS-008 Blocked by: – | 1. All prototype screens listed with screenshot 2. Tokens JSON produced 3. Component catalogue and per-screen specs written 4. Missing designs identified | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Manual review | docs/design/: 22 screenshots, design-tokens.json, LittleStory_Figma_Design_Details.md | 3 | Medium | Low | UI Integration & Visual Regression Engineer | Yes | Low | – (no code) |  |  | Done | Project owner (human) | Not required – design pack supplied | 18 screens / 22 states inventoried; tokens, typography, components, motion, a11y gaps extracted; 5 missing screens identified | None | N/A | Completed from supplied design pack: LittleStory_Figma_Design_Details.md, design-tokens.json, 22 screenshots. | NFR-10
LS-003 | Task | LS-EPIC-01 | Requirements catalogue, user journeys A–G and edge cases | Write docs/product/* (vision, FR/NFR from the Requirements sheet, journeys A–G incl. language change, edge cases, MVP scope) and docs/design/screen-inventory.md + screen-state-matrix.md. | – | Delivery clarity – avoids rework | High | Must | P1 | Docs | All | Design pack – all screens (docs/design/screens/) | LS-001, LS-002 | Blocks: LS-006 Blocked by: LS-001, LS-002 | 1. Every FR/NFR has ID, MoSCoW, source, screens, acceptance summary 2. Journeys map to SCR IDs 3. Edge cases include Kannada text expansion, empty states, cancel/retry 4. Unverified items marked as assumptions | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Doc review |  | 5 | High | Low | Product Manager / BA | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: docs/product/* | None | N/A |  | All FR/NFR
LS-004 | Task | LS-EPIC-01 | Resolve design gaps & open product decisions | Decision log for: LittleKatha→LittleStory rename in assets; 7 design languages vs EN/KN MVP; missing screens (SCR-19…23); app vs story language; reminders scheduling; demo subscription flag; gendered placeholder copy; greeting time-of-day; transition animations; swipe in onboarding. | – | Delivery clarity – avoids rework | High | Must | P1 | Docs / Design | SCR-19…SCR-23 | Design pack – all screens (docs/design/screens/) | LS-002 | Blocks: LS-046, LS-051, LS-111, LS-113, LS-114, LS-115 Blocked by: LS-002 | 1. Each open question in 'Risks & Questions' has an owner decision or explicit deferral 2. Decisions recorded in docs/project-management/decision-log.md 3. Affected tickets updated | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Doc review |  | 2 | Low | Medium | Technical Product Owner | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: docs/project-management/decision-log.md (D10, D13), docs/design/figma-audit.md | None | N/A | Blocks LS-046, LS-051, LS-111, LS-113, LS-114, LS-115. | FR-20, FR-22, FR-23, FR-25
LS-005 | Task | LS-EPIC-01 | CLAUDE.md and .github/copilot-instructions.md | Agent instructions mirrored for Claude Code and GitHub Copilot: architecture, no-hardcoding, EN/KN localization, testing, cross-platform, approval levels. | – | Delivery clarity – avoids rework | High | Must | P1 | Repo root | – | – | LS-001 | Blocks: – Blocked by: LS-001 | 1. Both files exist with consistent rules 2. Rules reference docs paths 3. Approval levels A–F stated | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: CLAUDE.md, .github/copilot-instructions.md Use tokens, string resources (EN+KN) and AppConfig only. | Doc review |  | 2 | Low | Low | Orchestrator | Yes | Medium | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: CLAUDE.md, .github/copilot-instructions.md | None | N/A |  | NFR-01, NFR-02, NFR-09
LS-006 | Task | LS-EPIC-01 | Prompt library (prompts/00–21) and per-ticket prompts | Create prompts listed in the Prompt Library sheet and prompts/tickets/LS-###.md for each ticket with scope, forbidden changes, l10n and stop conditions. | – | Delivery clarity – avoids rework | Medium | Must | P1 | prompts/ | – | – | LS-003, LS-008 | Blocks: – Blocked by: LS-003, LS-008 | 1. All prompt files exist and do not contradict the master prompt 2. Each ticket prompt includes forbidden-hardcoding rule and EN/KN requirement | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Doc review |  | 3 | Medium | Low | Documentation & Jira Backlog Manager | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: prompts/00–21, prompts/tickets/ (P2) | None | N/A
LS-007 | Task | LS-EPIC-01 | Commit backlog workbook and design reference pack to docs/ | Place this workbook at docs/project-management/ and the design pack at docs/design/ (screens/, design-tokens.json, LittleStory_Figma_Design_Details.md) so hyperlinks resolve. | – | Delivery clarity – avoids rework | Medium | Must | P1 | Docs | All | Design pack – all screens (docs/design/screens/) | LS-001 | Blocks: – Blocked by: LS-001 | 1. Workbook opens with all sheets and images 2. Screenshot hyperlinks resolve from docs/project-management/ 3. Committed on a docs branch via PR | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Open workbook; click 3 screenshot links |  | 1 | Low | Low | Documentation & Jira Backlog Manager | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: docs/ (design pack in PR #1) | None | N/A
LS-008 | Task | LS-EPIC-01 | Architecture ADRs (ADR-001…015) | Write ADRs listed in the Architecture Decisions sheet with options, rationale, consequences; status Proposed until owner approval. | – | Delivery clarity – avoids rework | High | Must | P1 | Docs / Architecture | – | – | LS-001, LS-002 | Blocks: LS-006, LS-030, LS-031 Blocked by: LS-001, LS-002 | 1. 15 ADRs in docs/architecture/adr/ 2. Each references affected tickets 3. Owner approves or comments | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Doc review |  | 3 | Medium | Low | Android Principal Architect | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: docs/architecture/adr/ADR-001…018 | None | N/A |  | NFR-05
LS-010 | Story | LS-EPIC-02 | Colour tokens → Compose theme | Implement all colours from design-tokens.json as named tokens: Material3 ColorScheme mapping + LittleStoryColors extension (night, night-surface, success-bg, favourite, story-art gradients, illustration colours). Single light theme with night surfaces (ADR-013). | As a developer, I want every colour as a named token so design changes happen in one place. | Visual fidelity and consistency | High | Must | P2 | :core:designsystem | All | Design pack – all screens (docs/design/screens/) | LS-031 | Blocks: LS-014, LS-015, LS-018, LS-150 Blocked by: LS-031 | 1. Every token in design-tokens.json exists exactly once in :core:designsystem 2. No hex literal outside token files (lint/detekt check) 3. Preview sheet shows all swatches | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: core/designsystem/theme/Color.kt Use tokens, string resources (EN+KN) and AppConfig only. | Unit: token map completeness test vs JSON · Screenshot: colour swatch preview |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | High | feature/LS-010-colour-tokens-compose-theme |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-01, NFR-10
LS-011 | Story | LS-EPIC-02 | Typography: DM Sans + Manrope + Kannada fallback, type scale | Bundle DM Sans (400–700) and Manrope (500–800) as res/font (OFL – record licence), add Noto Sans Kannada (OFL) fallback, define type scale from design (onboarding 29/1.12, hero 25/1.12, topbar 17/800, reader 16/1.95, chip 12/600, eyebrow 10/800 +1.6, nav 10/600). Kannada line-height adjustments. | As a Kannada-speaking parent, I want text to render clearly in my script. | Visual fidelity and consistency | High | Must | P2 | :core:designsystem | All | Design pack – all screens (docs/design/screens/) | LS-031 | Blocks: LS-014, LS-015 Blocked by: LS-031 | 1. All text styles from design spec available as theme tokens 2. Kannada renders with correct glyphs in every style 3. Licences listed in Help & about / docs 4. No inline TextStyle in feature code | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: core/designsystem/theme/Type.kt, res/font Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot: type specimen EN + KN at font scale 1.0 and 1.5 |  | 5 | High | Medium | Jetpack Compose UI Engineer | After deps | High | feature/LS-011-typography-dm-sans-manrope-kannada |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Layout risk | Missing |  | NFR-01, NFR-02
LS-012 | Story | LS-EPIC-02 | Shape, spacing, elevation and motion tokens | Radii (lg 24, md 18, sm 13, button 16, hero 26, sheet 32 top, chip 20, avatar 15/19), spacing scale, shadows (shadow, soft, primary-button, hero, create-nav), layout constants (topbar 68, bottom nav 76, content padding 20/16 compact), motion durations (twinkle 2.4/1.7/1.1 s, button .18 s, toggle .2 s, progress .2/.3 s). | – | Visual fidelity and consistency | High | Must | P2 | :core:designsystem | All | Design pack – all screens (docs/design/screens/) | LS-031 | Blocks: LS-015, LS-018 Blocked by: LS-031 | 1. Tokens defined once in designsystem 2. Compact (≤360dp) and tall (≥900dp) variants handled via window size, not hardcoded checks 3. Reduced-motion flag disables infinite twinkle | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: core/designsystem/theme/Dimens.kt, Shape.kt, Motion.kt Use tokens, string resources (EN+KN) and AppConfig only. | Unit: token values · Screenshot: spacing/shape preview |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | High | feature/LS-012-shape-spacing-elevation-and-motion |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-01, NFR-04
LS-013 | Story | LS-EPIC-02 | Icon set (21 line icons) as vector drawables | Recreate icons home, compass, plus, book, user, bell, search, heart, download, play, pause, back, chevron, clock, check, close, edit, moon, settings, volume (24×24, 1.8 stroke, round caps) + filled variants for active heart/download. Add proper rewind-15/forward-15 icons (replaces overlapping glyphs). | – | Visual fidelity and consistency | Medium | Must | P2 | :core:designsystem | All | Design pack – all screens (docs/design/screens/) | LS-031 | Blocks: LS-019, LS-094 Blocked by: LS-031 | 1. All icons in res/drawable with consistent naming ic_* 2. Auto-mirroring set where directional (back, chevron) for RTL 3. Icon catalogue preview | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot: icon catalogue |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-013-icon-set-21-line-icons |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-10
LS-014 | Story | LS-EPIC-02 | LittleStory brand mark composable (default + light) | Rebuild the CSS logo symbol (skewed book outline, inner L curve, crescent, yellow ✦) + 'LittleStory' wordmark (Manrope 800, 18sp). Replace all 'LittleKatha' references. Wordmark text from string resource. | – | Visual fidelity and consistency | Medium | Must | P2 | :core:designsystem | SCR-01, SCR-03, SCR-04a, SCR-12, SCR-13 | SCR-01 Onboarding (3 slides) → 01-onboarding-1-every-day-has-a-story.jpg, 02-onboarding-2-your-child-the-hero.jpg, 03-onboarding-3-listen-dream-repeat.jpg SCR-03 Home → 05-home.jpg SCR-04a Discover → 06-discover.jpg SCR-12 My Stories → 14-my-stories.jpg SCR-13 Profile (settings hub) → 15-profile-settings.jpg | LS-010, LS-011 | Blocks: LS-060 Blocked by: LS-010, LS-011 | 1. Brand mark matches screenshot geometry with new name 2. Light variant for night backgrounds 3. No 'LittleKatha' anywhere in code/resources | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot: brand mark default/light |  | 2 | Low | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-014-littlestory-brand-mark-composable-default |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing | Screenshots still show LittleKatha (pre-rename).
LS-015 | Story | LS-EPIC-02 | Buttons and IconButton components | Button primary/secondary/ghost (52dp, radius 16, optional leading icon, press scale .98, disabled 45%), IconButton 42dp visual with ≥48dp touch target, active favourite style (#9D3158 on #FFEDF2). | – | Visual fidelity and consistency | High | Must | P2 | :core:designsystem | All | Design pack – all screens (docs/design/screens/) | LS-010, LS-011, LS-012 | Blocks: LS-016, LS-017, LS-018, LS-019, LS-020 Blocked by: LS-010, LS-011, LS-012 | 1. All variants + disabled + pressed previews 2. Touch target ≥48dp 3. contentDescription required parameter for IconButton | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Compose UI test: click/disabled · Screenshot EN/KN long label |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-015-buttons-and-iconbutton-components |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-04
LS-016 | Story | LS-EPIC-02 | Form components: text field, select, chips, segmented, toggle, search, tabs | Form card inputs (48dp, radius 13, lavender focus ring), dropdown select, chips single/multi (selected = soft-lavender + check), segmented control, toggle switch (43×25 visual, role switch), search field with clear, pill tabs. | – | Visual fidelity and consistency | High | Must | P2 | :core:designsystem | SCR-02, SCR-04a, SCR-07, SCR-12, SCR-13, SCR-16 | SCR-02 Setup – Child profile → 04-setup-profile.jpg SCR-04a Discover → 06-discover.jpg SCR-07 Create a Story → 07-create-story.jpg, 08-create-story-more-options-and-error.jpg SCR-12 My Stories → 14-my-stories.jpg SCR-13 Profile (settings hub) → 15-profile-settings.jpg SCR-16 Bedtime Reminder → 17-bedtime-reminder.jpg | LS-015 | Blocks: LS-020, LS-061, LS-071, LS-080, LS-100, LS-110 Blocked by: LS-015 | 1. Each component exposes selected/checked semantics 2. Focus states visible 3. Long Kannada labels wrap/scroll without clipping | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Compose UI tests for state changes · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-016-form-components-text-field-select |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Layout risk | Missing |  | NFR-04
LS-017 | Story | LS-EPIC-02 | Feedback components: bottom sheet, dialog, toast, empty state, notes banner, progress bars | Bottom sheet (handle, rows, cancel, dim overlay), centred dialog with success icon, toast/snackbar, empty state, green trust/notes banner, progress bars (reading 3dp, generation gradient, playback slider, storage). | – | Visual fidelity and consistency | High | Must | P2 | :core:designsystem | SCR-04b, SCR-08, SCR-11b, SCR-12, SCR-15, SCR-16, SCR-17 | SCR-04b Discover – No results (empty state) → 06-discover.jpg SCR-08 Generating + Paused → 09-generating.jpg SCR-11b Player – Sleep timer sheet → 13-player-sleep-timer-sheet.jpg SCR-12 My Stories → 14-my-stories.jpg SCR-15 Subscription (demo) + dialog → 16-subscription.jpg SCR-16 Bedtime Reminder → 17-bedtime-reminder.jpg SCR-17 Offline Downloads → 18-offline-downloads.jpg | LS-015 | Blocks: LS-020, LS-060, LS-072, LS-083, LS-092, LS-101, LS-113 Blocked by: LS-015 | 1. Sheet/dialog trap focus and dismiss on back 2. Toast duration from config 3. Progress exposes progress semantics | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Compose UI tests · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-017-feedback-components-bottom-sheet-dialog |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-04
LS-018 | Story | LS-EPIC-02 | Story components: StoryArt, StoryCard, ListStoryRow, ContinueCard, SectionHeader, Avatar | StoryArt drawn in Compose (gradient 145°, crescent moon, stars, hill, figure + motifs elephant/cricket/moon/forest/space/festival) driven by story data; StoryCard (2 sizes), ListStoryRow, ContinueCard, SectionHeader, CSS-style Avatar with selected outline. | – | Visual fidelity and consistency | High | Must | P2 | :core:ui | SCR-03, SCR-04a, SCR-05, SCR-06, SCR-09, SCR-10, SCR-11a, SCR-12, SCR-17 | SCR-03 Home → 05-home.jpg SCR-04a Discover → 06-discover.jpg SCR-05 Category (Indian Tales) → 21-category-indian-tales.jpg SCR-06 Story Detail → 22-story-detail.jpg SCR-09 Story Ready → 10-story-ready.jpg SCR-10 Reader → 11-reader.jpg SCR-11a Player → 12-player.jpg SCR-12 My Stories → 14-my-stories.jpg SCR-17 Offline Downloads → 18-offline-downloads.jpg | LS-010, LS-012, LS-015 | Blocks: LS-020, LS-070, LS-071, LS-073, LS-074, LS-084, LS-090, LS-092, LS-100, LS-101 Blocked by: LS-010, LS-012, LS-015 | 1. All six motifs render matching screenshots 2. Art colours come from tokens/story data, not literals 3. Cards announce title, category, duration, favourite state | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot: each motif + card variants EN/KN long title |  | 8 | Very High | Medium | Jetpack Compose UI Engineer | After deps | Low | feature/LS-018-story-components-storyart-storycard-liststoryrow |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Layout risk | Missing | ADR-010 (Canvas vs vector). | NFR-10
LS-019 | Story | LS-EPIC-02 | Navigation chrome: TopBar, BottomNav, sticky action bars | TopBar (back or brand, centred title, right action, 68dp), BottomNav 5 tabs with active pill and raised Create tile (48×40, 5dp ring), sticky single/dual action bars, window insets. | – | Visual fidelity and consistency | High | Must | P2 | :core:ui | All | Design pack – all screens (docs/design/screens/) | LS-013, LS-015 | Blocks: LS-020, LS-050 Blocked by: LS-013, LS-015 | 1. BottomNav labels fit in Kannada at 10sp (or approved fallback) 2. Insets correct with edge-to-edge 3. Selected tab announced | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot EN/KN · UI test tab selection |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | Medium | feature/LS-019-navigation-chrome-topbar-bottomnav-sticky |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Layout risk | Missing |  | NFR-04
LS-020 | Task | LS-EPIC-02 | Design-system catalogue & screenshot baselines (EN/KN) | Preview catalogue screen (debug only) + screenshot baselines for all components in EN, KN and pseudo-locale. | – | Visual fidelity and consistency | Medium | Should | P2 | :core:designsystem | – | – | LS-015, LS-016, LS-017, LS-018, LS-019, LS-035 | Blocks: – Blocked by: LS-015, LS-016, LS-017, LS-018, LS-019, LS-035 | 1. Baselines committed and reviewed by owner 2. Catalogue excluded from release build | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot tests |  | 3 | Medium | Low | UI Integration & Visual Regression Engineer | After deps | Low | feature/LS-020-design-system-catalogue-screenshot-baselines |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-10
LS-030 | Task | LS-EPIC-03 | Project baseline: Gradle wrapper, version catalog, JDK toolchain, .gitattributes | Verify/establish gradlew + gradlew.bat (exec bit), libs.versions.toml, JDK toolchain, minSdk/targetSdk decision, .gitattributes (LF; CRLF for .bat), .gitignore (local.properties, IDE), UTF-8. | – | Maintainable, testable base | Highest | Must | P2 | Build | – | – | LS-001, LS-008, LS-009, LS-039 | Blocks: LS-031, LS-130, LS-132 Blocked by: LS-001, LS-008 | 1. ./gradlew and gradlew.bat assembleDebug succeed on macOS and Windows 2. No machine-specific paths committed 3. No whole-file line-ending diffs | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: settings.gradle.kts, gradle/libs.versions.toml, .gitattributes Use tokens, string resources (EN+KN) and AppConfig only. | Build on both OSes |  | 3 | Medium | Low | Build, Gradle & CI/CD Engineer | No | High | feature/LS-030-project-baseline-gradle-wrapper-version |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-09
LS-031 | Task | LS-EPIC-03 | Module structure + build-logic convention plugins | Create the 14 modules proposed in ADR-002 (:app, build-logic, :core:designsystem, :core:ui, :core:common, :domain, :data, :feature:onboarding/home/discover/create/reader/library/settings) and convention plugins for shared Android/Compose/test config. | – | Maintainable, testable base | Highest | Must | P2 | Build | – | – | LS-030, LS-008 | Blocks: LS-010, LS-011, LS-012, LS-013, LS-032, LS-033, LS-034, LS-035, LS-037, LS-040, LS-050 Blocked by: LS-030, LS-008 | 1. Modules compile with dependency rules enforced 2. No duplicated Gradle blocks 3. Module graph documented | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: settings.gradle.kts, build-logic/ Use tokens, string resources (EN+KN) and AppConfig only. | Build; dependency-rule check |  | 5 | High | Low | Android Principal Architect | No | High | feature/LS-031-module-structure-build-logic-convention |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-05
LS-032 | Task | LS-EPIC-03 | Dependency injection (Hilt) and Application entry | Hilt setup, Application class, MainActivity single-activity host. | – | Maintainable, testable base | High | Must | P2 | :app | – | – | LS-031 | Blocks: – Blocked by: LS-031 | 1. App launches to placeholder 2. Hilt test runner configured | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: app/build.gradle.kts, AndroidManifest.xml Use tokens, string resources (EN+KN) and AppConfig only. | Instrumented smoke test |  | 2 | Low | Low | Senior Kotlin Engineer | After deps | High | feature/LS-032-dependency-injection-hilt-and-application |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A
LS-033 | Task | LS-EPIC-03 | Central configuration & feature flags (AppConfig) | Named config objects: validation limits (story text 500, age 3–12), simulated timings (generation +4%/120 ms, player tick), sleep-timer options, speed steps, storage quota (1 GB), toast duration, default language; feature flags: demoSubscription, simulatedAudio, simulatedDownloads, reminders; BuildConfig for version/env. | – | Maintainable, testable base | High | Must | P2 | :core:common | – | – | LS-031 | Blocks: LS-080, LS-082, LS-092, LS-113, LS-150 Blocked by: LS-031 | 1. No magic numbers in feature code for these values 2. Flags toggle features without code edits elsewhere 3. docs/architecture/configuration-and-constants.md lists every value | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: core/common/config/AppConfig.kt Use tokens, string resources (EN+KN) and AppConfig only. | Unit: config defaults |  | 3 | Medium | Low | Senior Kotlin Engineer | After deps | Medium | feature/LS-033-central-configuration-feature-flags-appconfig |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-01
LS-034 | Task | LS-EPIC-03 | Lint & static analysis rules (hardcoding, translations) | Lint: HardcodedText, MissingTranslation, SetTextI18n as errors; Detekt/ktlint (if approved) with MagicNumber and custom rule forbidding Color(0x…)/raw .dp in feature modules. | – | Maintainable, testable base | High | Must | P2 | Build | – | – | LS-031 | Blocks: LS-125, LS-130 Blocked by: LS-031 | 1. Introducing a hardcoded string or hex colour in a feature fails the build 2. Baseline file empty | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: lint.xml, detekt.yml Use tokens, string resources (EN+KN) and AppConfig only. | Negative test: deliberately add hardcoded string → build fails |  | 3 | Medium | Low | Code Quality & Maintainability Reviewer | After deps | Medium | feature/LS-034-lint-static-analysis-rules-hardcoding |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-01, NFR-02
LS-035 | Task | LS-EPIC-03 | Test infrastructure (unit, UI, screenshot) | JUnit, MockK, coroutines-test, Turbine, Compose UI test, screenshot tool per ADR-011; locale-parameterised test helpers (en, kn, en-XA). | – | Maintainable, testable base | High | Must | P2 | Build / test | – | – | LS-031 | Blocks: LS-020, LS-122 Blocked by: LS-031 | 1. Sample test of each kind passes on CI 2. Screenshot tests run per locale | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: gradle/libs.versions.toml Use tokens, string resources (EN+KN) and AppConfig only. | CI run |  | 3 | Medium | Low | Android Testing & Automation Engineer | After deps | Medium | feature/LS-035-test-infrastructure-unit-ui-screenshot |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A
LS-036 | Task | LS-EPIC-03 | Mock data sources: per-language JSON assets + loader | assets/mock/stories_{en,kn}.json, categories, notifications, plans, profiles; loader with English fallback; stable IDs identical across languages; seed covers long titles, missing KN translation, empty library. | – | Maintainable, testable base | High | Must | P2 | :data | All | Design pack – all screens (docs/design/screens/) | LS-037 | Blocks: LS-044, LS-070, LS-071, LS-073, LS-074, LS-082, LS-090, LS-112 Blocked by: LS-037 | 1. Six design stories + reader pages load in EN 2. Missing KN entry falls back to EN 3. No mock content in composables/ViewModels | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit: loader + fallback |  | 5 | High | Low | Data & Persistence Engineer | After deps | Low | feature/LS-036-mock-data-sources-per-language |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Content | Missing |  | NFR-06, FR-21
LS-037 | Task | LS-EPIC-03 | Domain models & repository interfaces | Story, StoryPage, Category, ChildProfile, Avatar, StoryCreationRequest, GenerationState, ReadingProgress, PlaybackState, Download, ReminderSettings, Notification, Plan, SupportedLanguage; repository interfaces (Catalog, Profiles, Favourites, Library, Generation, Progress, Downloads, Preferences, Notifications, Subscription). | – | Maintainable, testable base | Highest | Must | P2 | :domain | – | – | LS-031 | Blocks: LS-036, LS-038, LS-082, LS-140 Blocked by: LS-031 | 1. Domain has no Android/Compose imports 2. Models documented in docs/architecture/data-models.md | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: domain/model/*, domain/repository/* Use tokens, string resources (EN+KN) and AppConfig only. | Unit: model validation |  | 5 | High | Low | Android Principal Architect | After deps | High | feature/LS-037-domain-models-repository-interfaces |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-05
LS-038 | Task | LS-EPIC-03 | Local persistence (DataStore + Room per ADR-004) | DataStore: settings, active profile, language default, reader text size; Room: profiles, favourites, created stories, progress, downloads, notifications read state. | – | Maintainable, testable base | High | Must | P2 | :data | – | – | LS-037 | Blocks: LS-051, LS-062, LS-075, LS-091, LS-101, LS-111 Blocked by: LS-037 | 1. Data survives process death 2. In-memory Room tests 3. No child data logged | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Room DAO tests · DataStore tests |  | 5 | High | Low | Data & Persistence Engineer | After deps | Medium | feature/LS-038-local-persistence-datastore-room-per |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-07, NFR-11
LS-040 | Story | LS-EPIC-14 | Localization foundation: EN/KN resources, locale switching, language registry, UiText | values/ + values-kn/ per module, res/xml/locales_config.xml, manifest reference, AppCompatDelegate.setApplicationLocales, SupportedLanguage registry (tag, native name 'English'/'ಕನ್ನಡ', enabled), UiText sealed type for ViewModels, supportsRtl. | As a parent, I want to use the app in Kannada so my family understands it. | Reach Kannada-speaking families | Highest | Must | P2 | :core:common / :core:ui | All | Design pack – all screens (docs/design/screens/) | LS-031 | Blocks: LS-041, LS-042, LS-043, LS-045, LS-046, LS-048, LS-081, LS-150 Blocked by: LS-031 | 1. Switching language updates UI without restart and persists 2. Registry is the only list of languages 3. ViewModels hold no translated text | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: locales_config.xml, SupportedLanguage.kt Use tokens, string resources (EN+KN) and AppConfig only. | Unit: registry · UI: switch EN→KN→EN |  | 5 | High | Low | Accessibility, Localization & i18n Engineer | After deps | High | feature/LS-040-localization-foundation-en-kn-resources |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-20, NFR-02, NFR-03
LS-041 | Task | LS-EPIC-14 | Translation completeness check (key & format-arg parity) in Gradle/CI | Task that fails when a key in values/ is missing in values-kn/ (and any future values-xx/) or format args differ; also checks mock JSON has every story ID per language or explicit fallback. | – | Reach Kannada-speaking families | High | Must | P2 | Build | – | – | LS-040 | Blocks: LS-048, LS-130 Blocked by: LS-040 | 1. Missing KN key fails CI with clear message 2. Mismatched %1$s fails CI | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Negative tests |  | 2 | Low | Low | Build, Gradle & CI/CD Engineer | After deps | Low | feature/LS-041-translation-completeness-check-key-format |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-02
LS-042 | Task | LS-EPIC-14 | Pseudo-locales & RTL readiness | Enable en-XA/ar-XB in debug; start/end everywhere; autoMirrored icons. | – | Reach Kannada-speaking families | Medium | Should | P2 | :app | – | – | LS-040 | Blocks: – Blocked by: LS-040 | 1. Key screens render under en-XA without clipping 2. ar-XB mirrors layout correctly | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot en-XA, ar-XB |  | 1 | Low | Low | Accessibility, Localization & i18n Engineer | Yes | Low | feature/LS-042-pseudo-locales-rtl-readiness |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-03
LS-043 | Task | LS-EPIC-14 | Kannada UI strings (draft) + glossary | Populate values-kn for all keys in the Translation Tracking sheet; docs/localization/glossary.md for child-friendly terms (story, bedtime, favourite…). Mark every KN value 'Needs native review'. | – | Reach Kannada-speaking families | High | Must | P6 | Resources | All | Design pack – all screens (docs/design/screens/) | LS-040 | Blocks: LS-047 Blocked by: LS-040 | 1. 100% key coverage in KN 2. Glossary covers recurring terms 3. Translation Tracking sheet updated | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Translation completeness check |  | 5 | High | Medium | Accessibility, Localization & i18n Engineer | Yes | Low | feature/LS-043-kannada-ui-strings-draft-glossary |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | NFR-02
LS-044 | Task | LS-EPIC-14 | Kannada mock story content | Kannada titles, synopses, lessons, reader pages for the six design stories and notifications; stable IDs. | – | Reach Kannada-speaking families | High | Must | P4 | :data assets | SCR-06, SCR-09, SCR-10 | SCR-06 Story Detail → 22-story-detail.jpg SCR-09 Story Ready → 10-story-ready.jpg SCR-10 Reader → 11-reader.jpg | LS-036 | Blocks: LS-047 Blocked by: LS-036 | 1. All six stories readable in KN 2. One deliberate gap tests EN fallback (test data only) | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit: content loader per locale |  | 3 | Medium | Medium | Accessibility, Localization & i18n Engineer | Yes | Low | feature/LS-044-kannada-mock-story-content |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Content | Missing |  | FR-21
LS-045 | Story | LS-EPIC-14 | Language selection in Setup (registry-driven) | Setup language select lists only enabled registry languages (English, ಕನ್ನಡ) in their own script; selection sets app language and child default story language per LS-004 decision. | – | Reach Kannada-speaking families | High | Must | P3 | :feature:onboarding | SCR-02 | SCR-02 Setup – Child profile → 04-setup-profile.jpg | LS-040, LS-061 | Blocks: – Blocked by: LS-040, LS-061 | 1. Only EN/KN shown 2. Choosing ಕನ್ನಡ switches UI immediately 3. Selection persists | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test |  | 2 | Low | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-045-language-selection-in-setup-registry |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-20
LS-046 | Story | LS-EPIC-14 | Language preferences screen (from Profile) | New simple screen (design missing – SCR-20) listing registry languages with check; optionally separate story-language default per LS-004. | – | Reach Kannada-speaking families | High | Must | P6 | :feature:settings | SCR-20, SCR-13 | SCR-20 Language preferences → no design (missing) SCR-13 Profile (settings hub) → 15-profile-settings.jpg | LS-004, LS-040, LS-110 | Blocks: – Blocked by: LS-004, LS-040, LS-110 | 1. Reachable from Profile → Language preferences 2. Subtitle on Profile reflects current choice 3. Works with future languages without code change | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 3 | Medium | Medium | Jetpack Compose UI Engineer | After deps | Low | feature/LS-046-language-preferences-screen-from-profile |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing | Design missing – reuse settings-row pattern; owner to approve. | FR-20
LS-047 | Task | LS-EPIC-14 | Native Kannada review & sign-off | Fluent Kannada reviewer checks all strings and mock content in context (screenshots), updates statuses to Approved. | – | Reach Kannada-speaking families | High | Must | P7 | Resources | All | Design pack – all screens (docs/design/screens/) | LS-043, LS-044, LS-122 | Blocks: LS-133 Blocked by: LS-043, LS-044, LS-122 | 1. All KN rows 'Approved' 2. Issues logged and fixed | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Manual review |  | 3 | Medium | High | Accessibility, Localization & i18n Engineer | After deps | Low | feature/LS-047-native-kannada-review-sign-off |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A | Needs a named reviewer (risk R-12). | NFR-02
LS-048 | Task | LS-EPIC-14 | 'How to add a new language' guide + prompt | docs/localization/adding-a-new-language.md and prompts/20_ADD_NEW_LANGUAGE_PROMPT.md; dry-run with a pseudo language to prove no feature-code change. | – | Reach Kannada-speaking families | Medium | Must | P8 | Docs | – | – | LS-040, LS-041 | Blocks: – Blocked by: LS-040, LS-041 | 1. Dry run adds language with resources + registry + locales_config only | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Dry-run evidence |  | 1 | Low | Low | Accessibility, Localization & i18n Engineer | Yes | Low | feature/LS-048-how-to-add-a-new |  |  | To Do | Project owner (human) | Awaiting Approval B |  | None | N/A |  | NFR-03
LS-050 | Story | LS-EPIC-04 | Navigation graph with typed routes for all screens | Typed destinations for SCR-01…SCR-22; bottom-nav tabs with saved state; back behaviour per screen spec; deep-link targets for notifications. | – | Coherent app structure | Highest | Must | P3 | :app / navigation | All | Design pack – all screens (docs/design/screens/) | LS-019, LS-031 | Blocks: LS-051, LS-052, LS-060, LS-061, LS-070, LS-071, LS-073, LS-074, LS-080, LS-090, LS-110, LS-112 Blocked by: LS-019, LS-031 | 1. All prototype navigation paths work 2. Back from each screen matches spec 3. Routes defined in one place | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: AppNavHost.kt, Destinations.kt Use tokens, string resources (EN+KN) and AppConfig only. | UI navigation tests |  | 5 | High | Low | Navigation & Application State Engineer | No | High | feature/LS-050-navigation-graph-with-typed-routes |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-01
LS-051 | Story | LS-EPIC-04 | Splash screen & first-run routing | core-splashscreen; first-run flag routes to Onboarding else Home. | – | Coherent app structure | High | Must | P3 | :app | SCR-19 | SCR-19 Splash / launch → no design (missing) | LS-004, LS-050, LS-038 | Blocks: – Blocked by: LS-004, LS-050, LS-038 | 1. First launch → Onboarding; later → Home 2. No blank frame | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | UI test with cleared data |  | 2 | Low | Low | Navigation & Application State Engineer | After deps | Low | feature/LS-051-splash-screen-first-run-routing |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A | Design missing – needs owner approval of splash spec. | FR-25
LS-052 | Task | LS-EPIC-04 | Edge-to-edge & system bar styling | Dark icons on cream screens, light icons on night screens (Onboarding, Generating, Player, Subscription hero). | – | Coherent app structure | Medium | Must | P3 | :core:ui | All | Design pack – all screens (docs/design/screens/) | LS-050 | Blocks: – Blocked by: LS-050 | 1. Status/nav bar icons legible on every screen | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot per screen |  | 2 | Low | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-052-edge-to-edge-system-bar |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A
LS-060 | Story | LS-EPIC-05 | Onboarding – 3 slides | Implement SCR-01: night scene illustration, twinkle animation (reduced-motion aware), sheet with eyebrow/title/body, pager, Continue / Get Started, Skip. | As a new parent, I want a short intro so I understand what LittleStory does. | Personalised first-run experience | High | Must | P3 | :feature:onboarding | SCR-01 | SCR-01 Onboarding (3 slides) → 01-onboarding-1-every-day-has-a-story.jpg, 02-onboarding-2-your-child-the-hero.jpg, 03-onboarding-3-listen-dream-repeat.jpg | LS-050, LS-017, LS-014 | Blocks: LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-050, LS-017, LS-014 | 1. Copy matches design in EN; KN present 2. Continue advances; slide 3 shows Get Started → Setup 3. Skip → Setup 4. Pager announced | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test flow · Screenshot 3 slides EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-060-onboarding-3-slides |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-01
LS-061 | Story | LS-EPIC-05 | Setup – child profile form | Implement SCR-02 with ViewModel: fields, avatar picker, age 3–12, language (LS-045), interests multi-select, duration segmented, sticky CTA, Skip for now. Validation rules per LS-004. | As a parent, I want to set up my child's profile so stories feel personal. | Personalised first-run experience | High | Must | P3 | :feature:onboarding | SCR-02 | SCR-02 Setup – Child profile → 04-setup-profile.jpg | LS-016, LS-062, LS-050 | Blocks: LS-045, LS-063, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-016, LS-062, LS-050 | 1. Defaults as designed for demo data only (empty for real first run – decision) 2. CTA text includes child name via format arg 3. Profile saved and Home shows name | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | ViewModel unit tests · UI test · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-061-setup-child-profile-form |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-02, NFR-07
LS-062 | Story | LS-EPIC-05 | Profile repository & active-child state | ChildProfileRepository (Room/DataStore), active child flow consumed by Home, Create, Player labels. | – | Personalised first-run experience | High | Must | P3 | :data | SCR-02, SCR-14 | SCR-02 Setup – Child profile → 04-setup-profile.jpg SCR-14 Child Profiles → 20-child-profiles.jpg | LS-038 | Blocks: LS-061, LS-063, LS-070, LS-080, LS-110, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-038 | 1. Active child persists 2. Switching child updates all screens | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit + Room tests |  | 3 | Medium | Low | Data & Persistence Engineer | After deps | Low | feature/LS-062-profile-repository-active-child-state |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | FR-02, FR-03
LS-063 | Story | LS-EPIC-05 | Child Profiles – list, switch, edit, add | Implement SCR-14: privacy note, profile cards with Active/Switch, edit → Setup prefilled, Add child. | – | Personalised first-run experience | Medium | Should | P6 | :feature:settings | SCR-14 | SCR-14 Child Profiles → 20-child-profiles.jpg | LS-062, LS-061 | Blocks: LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-062, LS-061 | 1. Switch changes active child 2. Edit saves changes 3. Add creates new profile | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-063-child-profiles-list-switch-edit |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-03
LS-070 | Story | LS-EPIC-06 | Home screen | Implement SCR-03 with HomeViewModel: greeting, 'Stories for {child}', hero + Create CTA, Continue listening card (hidden if none), category tiles, 'Made for {child}' row with hearts, culture banner, bell/avatar actions. | As a parent, I want tonight's options at a glance so bedtime starts quickly. | Core browsing value | Highest | Must | P4 | :feature:home | SCR-03 | SCR-03 Home → 05-home.jpg | LS-018, LS-050, LS-062, LS-036 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-050, LS-062, LS-036 | 1. Matches screenshot EN 2. KN layout without clipping 3. All tap targets navigate per spec 4. Empty continue state handled | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | ViewModel unit · UI test · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-070-home-screen |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-04, FR-24
LS-071 | Story | LS-EPIC-06 | Discover – search, featured, filters, grid, rows | Implement SCR-04a: live search (locale-aware), featured card hidden while searching, filter chips, Popular grid, Bedtime favourites row. | – | Core browsing value | High | Must | P4 | :feature:discover | SCR-04a | SCR-04a Discover → 06-discover.jpg | LS-018, LS-016, LS-036, LS-050 | Blocks: LS-072, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-016, LS-036, LS-050 | 1. Search filters by title in EN and KN 2. Chip filters by category 3. 'Results for …' title while searching | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | ViewModel unit (filtering) · UI test · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-071-discover-search-featured-filters-grid |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-05
LS-072 | Story | LS-EPIC-06 | Discover – no-results empty state | Implement SCR-04b empty state; Clear search resets query and chip. | – | Core browsing value | Medium | Must | P4 | :feature:discover | SCR-04b | SCR-04b Discover – No results (empty state) → 06-discover.jpg | LS-071, LS-017 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-071, LS-017 | 1. Shown when no match 2. Clear search restores default | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test |  | 1 | Low | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-072-discover-no-results-empty-state |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-05
LS-073 | Story | LS-EPIC-06 | Category screen (generic, sortable) | Implement SCR-05 for any category id: hero (count plural, description), sort select, list rows with offline + heart. | – | Core browsing value | Medium | Should | P4 | :feature:discover | SCR-05 | SCR-05 Category (Indian Tales) → 21-category-indian-tales.jpg | LS-018, LS-036, LS-050 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-036, LS-050 | 1. Works for every category in mock data 2. Sort orders correct 3. '{n} stories' uses plurals | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | Unit: sort · UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-073-category-screen-generic-sortable |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-06
LS-074 | Story | LS-EPIC-06 | Story Detail screen | Implement SCR-06: cover, back/favourite/download, pill, metadata, synopsis, lesson panel, narration row, sticky Listen/Read. | – | Core browsing value | High | Must | P4 | :feature:discover | SCR-06 | SCR-06 Story Detail → 22-story-detail.jpg | LS-018, LS-036, LS-050, LS-075 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-036, LS-050, LS-075 | 1. Data-driven for any story id 2. Language tag reflects story language 3. Listen → Player, Read → Reader | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-074-story-detail-screen |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-07
LS-075 | Story | LS-EPIC-06 | Favourites (shared, persisted) | FavouritesRepository + toggle use case used by every story surface; optimistic UI, no duplicate writes. | – | Core browsing value | High | Must | P4 | :data / :domain | Multiple | Design pack – all screens (docs/design/screens/) | LS-038 | Blocks: LS-074, LS-100, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-038 | 1. Toggle on any screen reflects everywhere 2. Persists after restart 3. Rapid taps produce consistent state | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit + Room tests · UI test |  | 2 | Low | Low | Data & Persistence Engineer | After deps | Low | feature/LS-075-favourites-shared-persisted |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | FR-13
LS-080 | Story | LS-EPIC-07 | Create a Story – form | Implement SCR-07: intro, textarea with n/500 counter (limit from AppConfig), suggestion chips (neutral copy per LS-004), story hero selector, theme chips, safety note, CTA. | As a parent, I want to turn my child's day into a story. | Signature feature | Highest | Must | P4 | :feature:create | SCR-07 | SCR-07 Create a Story → 07-create-story.jpg, 08-create-story-more-options-and-error.jpg | LS-016, LS-062, LS-033, LS-050 | Blocks: LS-081, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-016, LS-062, LS-033, LS-050 | 1. Counter enforces limit 2. Suggestions fill text 3. Hero selector lists profiles | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | ViewModel unit · UI test · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-080-create-a-story-form |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-08
LS-081 | Story | LS-EPIC-07 | Create – more options & validation | Collapsible More options (mood, duration, story language EN/KN from registry), chevron rotation; empty-text error banner announced and cleared on typing. | – | Signature feature | High | Must | P4 | :feature:create | SCR-07 | SCR-07 Create a Story → 07-create-story.jpg, 08-create-story-more-options-and-error.jpg | LS-080, LS-040 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-080, LS-040 | 1. Empty submit shows error, no navigation 2. Typing clears error 3. Story language limited to EN/KN | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | Unit: validation · UI test · Screenshot error EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-081-create-more-options-validation |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-08, FR-21
LS-082 | Story | LS-EPIC-07 | Simulated generation repository & use case | Deterministic, cancellable generation: progress steps and stage thresholds (38/76%) from AppConfig; returns localized mock story for the request language; injectable clock for tests. | – | Signature feature | High | Must | P4 | :data / :domain | SCR-08, SCR-09 | SCR-08 Generating + Paused → 09-generating.jpg SCR-09 Story Ready → 10-story-ready.jpg | LS-037, LS-036, LS-033 | Blocks: LS-083, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126, LS-141 Blocked by: LS-037, LS-036, LS-033 | 1. Same input → same output 2. Cancel stops progress 3. Result saved to Created by Me | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit with test dispatcher |  | 3 | Medium | Low | AI Story Generation Integration Architect | Yes | Low | feature/LS-082-simulated-generation-repository-use-case |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | FR-09, FR-10, NFR-12
LS-083 | Story | LS-EPIC-07 | Generating screen + paused state | Implement SCR-08: night gradient, stars, magic book, progress %, stages, footnote, close → paused, Try again / Back to your idea, auto-advance. | – | Signature feature | High | Must | P4 | :feature:create | SCR-08 | SCR-08 Generating + Paused → 09-generating.jpg | LS-082, LS-017 | Blocks: LS-084, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-082, LS-017 | 1. Stages change at thresholds 2. Paused state per spec 3. Auto-advance to Story Ready | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test with fake repo · Screenshot EN/KN (progress, paused) |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-083-generating-screen-paused-state |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-09
LS-084 | Story | LS-EPIC-07 | Story Ready screen | Implement SCR-09: ribbon, cover with badge, metadata, synopsis, peek quote, Listen/Read, 'Saved to My Stories' row → My Stories Created tab. | – | Signature feature | High | Must | P4 | :feature:create | SCR-09 | SCR-09 Story Ready → 10-story-ready.jpg | LS-083, LS-018 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-083, LS-018 | 1. Shows generated story in selected language 2. Row opens My Stories on Created by Me | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-084-story-ready-screen |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-10
LS-090 | Story | LS-EPIC-08 | Reader screen | Implement SCR-10: page indicator, A−/A+ (0.9–1.3 step 0.1 from config), progress bar, title, cover on page 1, paragraph, prev/next disabled states, play → Player. | As a child, I want to read my story page by page with text I can see clearly. | Bedtime reading/listening | High | Must | P5 | :feature:reader | SCR-10 | SCR-10 Reader → 11-reader.jpg | LS-018, LS-036, LS-050 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-036, LS-050 | 1. Pagination and disabled states correct 2. Text size persists 3. Respects system font scale; KN line height | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | ViewModel unit · UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-090-reader-screen |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Layout risk | Missing |  | FR-11
LS-091 | Story | LS-EPIC-08 | Reading & listening progress persistence | ProgressRepository; Home continue card and My Stories recently played read from it. | – | Bedtime reading/listening | Medium | Should | P5 | :data | SCR-03, SCR-10, SCR-11a, SCR-12 | SCR-03 Home → 05-home.jpg SCR-10 Reader → 11-reader.jpg SCR-11a Player → 12-player.jpg SCR-12 My Stories → 14-my-stories.jpg | LS-038 | Blocks: LS-092, LS-100, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-038 | 1. Resume opens last page/position 2. Progress % shown correctly | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit + Room tests |  | 2 | Low | Low | Data & Persistence Engineer | After deps | Low | feature/LS-091-reading-listening-progress-persistence |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | FR-24
LS-092 | Story | LS-EPIC-08 | Simulated audio player | Implement SCR-11a: playback state machine (play/pause, seek, ±15 s, chapters, speed cycle, volume), download/favourite toggles, 'Story text' → Reader; visible 'simulated narration' label per NFR-12. | – | Bedtime reading/listening | High | Should | P5 | :feature:reader | SCR-11a | SCR-11a Player → 12-player.jpg | LS-018, LS-017, LS-091, LS-033 | Blocks: LS-093, LS-094, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-017, LS-091, LS-033 | 1. Controls behave as spec 2. Timer text formatted mm:ss 3. Simulation clearly indicated | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | Unit: state machine · UI test · Screenshot EN/KN |  | 5 | High | Medium | Jetpack Compose UI Engineer | After deps | Low | feature/LS-092-simulated-audio-player |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-12, NFR-12
LS-093 | Story | LS-EPIC-08 | Sleep timer bottom sheet | Implement SCR-11b with options from AppConfig; selected label replaces 'Sleep timer'; simulated stop at end. | – | Bedtime reading/listening | Medium | Should | P5 | :feature:reader | SCR-11b | SCR-11b Player – Sleep timer sheet → 13-player-sleep-timer-sheet.jpg | LS-092 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-092 | 1. Selecting option closes sheet and updates button 2. Cancel/tap outside dismisses | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 2 | Low | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-093-sleep-timer-bottom-sheet |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-12
LS-094 | Bug | LS-EPIC-08 | Fix overlapping 15 s rewind/forward glyphs | Design defect: '15' text and ↶/↷ glyphs overlap. Use dedicated icons from LS-013. | – | Bedtime reading/listening | Medium | Must | P5 | :feature:reader | SCR-11a | SCR-11a Player → 12-player.jpg | LS-092, LS-013 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-092, LS-013 | 1. Icons legible, labelled 'Rewind 15 seconds'/'Forward 15 seconds' | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | Screenshot |  | 1 | Low | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-094-fix-overlapping-15-s-rewind |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-04
LS-100 | Story | LS-EPIC-09 | My Stories library | Implement SCR-12: search, tabs All/Created by Me/Downloaded/Favourites, recently played card, collection list, two empty states, download icon → Downloads. | – | Re-engagement | High | Must | P5 | :feature:library | SCR-12 | SCR-12 My Stories → 14-my-stories.jpg | LS-018, LS-016, LS-075, LS-091 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-018, LS-016, LS-075, LS-091 | 1. Each tab shows correct subset 2. Empty states per tab 3. Search within tab | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | ViewModel unit · UI test · Screenshot EN/KN (each tab + empties) |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-100-my-stories-library |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-14
LS-101 | Story | LS-EPIC-09 | Simulated downloads + Offline Downloads screen | DownloadsRepository (simulated sizes), toggle from Detail/Player/Story Ready; SCR-17 storage card, list, remove, empty, tip. | – | Re-engagement | Medium | Could | P6 | :feature:library | SCR-17 | SCR-17 Offline Downloads → 18-offline-downloads.jpg | LS-038, LS-018, LS-017 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-038, LS-018, LS-017 | 1. Download toggles reflect everywhere 2. Storage total computed 3. Remove updates list | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | Unit · UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-101-simulated-downloads-offline-downloads-screen |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-15, NFR-12
LS-110 | Story | LS-EPIC-10 | Profile / settings hub | Implement SCR-13: parent card, CHILDREN / EXPERIENCE / LITTLESTORY groups, rows with separate toggle targets (no nested interactive), subtitles from live data, footer. | – | Parent trust and control | High | Must | P6 | :feature:settings | SCR-13 | SCR-13 Profile (settings hub) → 15-profile-settings.jpg | LS-016, LS-050, LS-062 | Blocks: LS-046, LS-111, LS-114, LS-115, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-016, LS-050, LS-062 | 1. Toggles independent from row navigation 2. Subtitles reflect real settings 3. Rows route to real screens (or disabled per LS-004) | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 5 | High | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-110-profile-settings-hub |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-16, NFR-04
LS-111 | Story | LS-EPIC-10 | Bedtime Reminder settings | Implement SCR-16: toggle, time picker (locale time), day buttons with full-name a11y labels, quiet row, save + toast; persist locally. Scheduling per LS-004 decision. | – | Parent trust and control | Medium | Could | P6 | :feature:settings | SCR-16 | SCR-16 Bedtime Reminder → 17-bedtime-reminder.jpg | LS-110, LS-038, LS-004 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-110, LS-038, LS-004 | 1. Disabling disables time & days 2. Saved values persist 3. Toast shows formatted time | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | Unit · UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-111-bedtime-reminder-settings |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-17
LS-112 | Story | LS-EPIC-10 | Notifications inbox (mock) | Implement SCR-18 from per-language mock data: sections, unread dot + semantics, mark all read, deep links; empty state per LS-004. | – | Parent trust and control | Low | Could | P6 | :feature:settings | SCR-18 | SCR-18 Notifications → 19-notifications.jpg | LS-050, LS-036 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-050, LS-036 | 1. Mark all read clears dots 2. Each row deep-links correctly | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 2 | Low | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-112-notifications-inbox-mock |  |  | To Do | Project owner (human) | Awaiting Approval C |  | Content | Missing |  | FR-18
LS-113 | Story | LS-EPIC-10 | Demo subscription (feature-flagged) + dialog | Implement SCR-15 behind demoSubscription flag: hero, benefits, plans from mock data with locale currency format, 'Illustrative pricing only' note, confirmation dialog, no billing. | – | Parent trust and control | Low | Could | P6 | :feature:settings | SCR-15 | SCR-15 Subscription (demo) + dialog → 16-subscription.jpg | LS-017, LS-033, LS-004 | Blocks: LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 Blocked by: LS-017, LS-033, LS-004 | 1. No payment code or permission 2. Flag off hides entry row 3. Prices formatted for locale | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Screenshot EN/KN |  | 3 | Medium | Low | Jetpack Compose UI Engineer | Yes | Low | feature/LS-113-demo-subscription-feature-flagged-dialog |  |  | To Do | Project owner (human) | Awaiting Approval C |  | New strings | Missing |  | FR-19, NFR-12
LS-114 | Story | LS-EPIC-10 | Privacy & parent controls screen | SCR-21 (design missing): explain local-only data, delete all local data action with confirmation. | – | Parent trust and control | Medium | Should | P6 | :feature:settings | SCR-21 | SCR-21 Privacy & parent controls → no design (missing) | LS-004, LS-110 | Blocks: LS-126 Blocked by: LS-004, LS-110 | 1. Content approved by owner 2. Delete clears profiles, favourites, progress, downloads | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test · Unit: data wipe |  | 3 | Medium | Low | Android Security & Privacy Reviewer | After deps | Low | feature/LS-114-privacy-parent-controls-screen |  |  | Blocked | Project owner (human) | Awaiting Approval C |  | New strings | Missing | Blocked: design and content missing (LS-004). | FR-22, NFR-07
LS-115 | Story | LS-EPIC-10 | Help & about screen | SCR-22 (design missing): version from BuildConfig, font licences, help text. | – | Parent trust and control | Low | Could | P6 | :feature:settings | SCR-22 | SCR-22 Help & about → no design (missing) | LS-004, LS-110 | Blocks: LS-126 Blocked by: LS-004, LS-110 | 1. Version shown from BuildConfig 2. Licences listed | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. UiState + StateFlow; UiText for messages; preview in EN/KN. | UI test |  | 1 | Low | Low | Jetpack Compose UI Engineer | After deps | Low | feature/LS-115-help-about-screen |  |  | Blocked | Project owner (human) | Awaiting Approval C |  | New strings | Missing | Blocked: design missing (LS-004). | FR-23
LS-120 | Task | LS-EPIC-11 | Unit-test coverage gate for ViewModels & use cases | Ensure each ViewModel/use case has tests; report coverage; agree threshold. | – | Release confidence | High | Must | P7 | All | – | – | LS-070…LS-113 | Blocks: – Blocked by: LS-070, LS-071, LS-072, LS-073, LS-074, LS-075, LS-080, LS-081, LS-082, LS-083, LS-084, LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101, LS-110, LS-111, LS-112, LS-113 | 1. Coverage report in CI 2. Agreed threshold met | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Unit |  | 3 | Medium | Low | Android Testing & Automation Engineer | After deps | Low | feature/LS-120-unit-test-coverage-gate-for |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-05
LS-121 | Task | LS-EPIC-11 | End-to-end journey tests A–G (EN & KN) | Automate journeys A (first run), B (discover & read), C (create), D (revisit), E (parent controls), F (audio), G (change language). | – | Release confidence | Highest | Must | P7 | All | All | Design pack – all screens (docs/design/screens/) | LS-060…LS-113 | Blocks: LS-133 Blocked by: LS-060, LS-061, LS-062, LS-063, LS-070, LS-071, LS-072, LS-073, LS-074, LS-075, LS-080, LS-081, LS-082, LS-083, LS-084, LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101, LS-110, LS-111, LS-112, LS-113 | 1. All journeys pass in en and kn | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Instrumented UI |  | 5 | High | Low | Android Testing & Automation Engineer | After deps | Low | feature/LS-121-end-to-end-journey-tests |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | All Must FR
LS-122 | Task | LS-EPIC-11 | Screenshot regression suite – 22 design states × EN/KN | Baselines for every captured design state in EN and KN (plus en-XA spot checks), compared against design pack. | – | Release confidence | High | Must | P7 | All | All | Design pack – all screens (docs/design/screens/) | LS-035, LS-060…LS-113 | Blocks: LS-047, LS-124, LS-133 Blocked by: LS-060, LS-061, LS-062, LS-063, LS-070, LS-071, LS-072, LS-073, LS-074, LS-075, LS-080, LS-081, LS-082, LS-083, LS-084, LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101, LS-110, LS-111, LS-112, LS-113, LS-035 | 1. Baselines reviewed by owner 2. Diffs fail CI | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Screenshot |  | 5 | High | Low | UI Integration & Visual Regression Engineer | After deps | Low | feature/LS-122-screenshot-regression-suite-22-design |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-10
LS-123 | Task | LS-EPIC-11 | Accessibility audit & fixes | Measure contrast (#716B80 at 10–12sp, #817B8D nav labels), 48dp targets (chips, 42dp icon buttons), selected-state semantics for chips/day picker, focus visibility, reduced motion, TalkBack in EN and KN. | – | Release confidence | High | Must | P7 | All | All | Design pack – all screens (docs/design/screens/) | LS-060…LS-113 | Blocks: LS-133 Blocked by: LS-060, LS-061, LS-062, LS-063, LS-070, LS-071, LS-072, LS-073, LS-074, LS-075, LS-080, LS-081, LS-082, LS-083, LS-084, LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101, LS-110, LS-111, LS-112, LS-113 | 1. All Must a11y issues fixed or accepted by owner 2. Report in docs/design/accessibility-spec.md | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Accessibility Scanner · TalkBack manual |  | 5 | High | Medium | Accessibility, Localization & i18n Engineer | After deps | Low | feature/LS-123-accessibility-audit-fixes |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-04
LS-124 | Task | LS-EPIC-11 | Visual fidelity review vs design pack | Screen-by-screen comparison with severity and defect tickets. | – | Release confidence | High | Must | P7 | All | All | Design pack – all screens (docs/design/screens/) | LS-122 | Blocks: – Blocked by: LS-122 | 1. Report per screen 2. Blocker/High fixed | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Manual + screenshot |  | 3 | Medium | Low | UI Integration & Visual Regression Engineer | After deps | Low | feature/LS-124-visual-fidelity-review-vs-design |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-10
LS-125 | Task | LS-EPIC-15 | Maintainability review – hardcoded values audit | Audit for hardcoded strings, colours, dims, routes, limits; duplication; config placement. | – | Cheap future changes | High | Must | P7 | All | – | – | LS-034, LS-060…LS-113 | Blocks: – Blocked by: LS-060, LS-061, LS-062, LS-063, LS-070, LS-071, LS-072, LS-073, LS-074, LS-075, LS-080, LS-081, LS-082, LS-083, LS-084, LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101, LS-110, LS-111, LS-112, LS-113, LS-034 | 1. Zero hardcoded values in feature modules 2. Findings fixed | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Static analysis report |  | 2 | Low | Low | Code Quality & Maintainability Reviewer | After deps | Low | feature/LS-125-maintainability-review-hardcoded-values-audit |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-01
LS-126 | Task | LS-EPIC-11 | Security & privacy review + threat model | docs/security/*: no network/analytics, no secrets, no child data in logs, backup rules, permissions minimal. | – | Release confidence | High | Must | P7 | All | – | – | LS-060…LS-115 | Blocks: LS-133 Blocked by: LS-060, LS-061, LS-062, LS-063, LS-070, LS-071, LS-072, LS-073, LS-074, LS-075, LS-080, LS-081, LS-082, LS-083, LS-084, LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101, LS-110, LS-111, LS-112, LS-113, LS-114, LS-115 | 1. Threat model and checklist complete 2. Findings resolved | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Manual review · lint security checks |  | 3 | Medium | Low | Android Security & Privacy Reviewer | After deps | Low | feature/LS-126-security-privacy-review-threat-model |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A |  | NFR-07
LS-130 | Task | LS-EPIC-12 | GitHub Actions PR workflow | Build, unit tests, lint, translation completeness, screenshot verify on PRs to development. | – | Repeatable delivery | High | Must | P2 | .github/workflows | – | – | LS-030, LS-034, LS-041 | Blocks: – Blocked by: LS-030, LS-034, LS-041 | 1. Required checks run on every PR 2. No secrets in workflow | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Shared files: .github/workflows/ci.yml Use tokens, string resources (EN+KN) and AppConfig only. | CI run |  | 3 | Medium | Low | Build, Gradle & CI/CD Engineer | After deps | Medium | feature/LS-130-github-actions-pr-workflow |  |  | To Do | Project owner (human) | Awaiting Approval C |  | None | N/A
LS-131 | Task | LS-EPIC-12 | Branch strategy, PR template, CODEOWNERS | Create development branch, PR template (ticket, AC, EN/KN screenshots, tests), CODEOWNERS; owner sets protections (Approval D). | – | Repeatable delivery | High | Must | P1 | .github | – | – | LS-001 | Blocks: – Blocked by: LS-001 | 1. development branch exists 2. PR template used | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Open test PR |  | 1 | Low | Low | Release & Deployment Coordinator | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: .github/pull_request_template.md, .github/CODEOWNERS (development branch awaits owner, D2) | None | N/A
LS-132 | Task | LS-EPIC-12 | Build & run docs (Windows + macOS), release checklist, known limitations | docs/release/*. | – | Repeatable delivery | Medium | Must | P8 | Docs | – | – | LS-030 | Blocks: – Blocked by: LS-030 | 1. A new developer builds on Windows and macOS following the doc | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Doc walkthrough |  | 2 | Low | Low | Release & Deployment Coordinator | Yes | Low | feature/LS-132-build-run-docs-windows-macos |  |  | To Do | Project owner (human) | Awaiting Approval B |  | None | N/A |  | NFR-09
LS-133 | Task | LS-EPIC-12 | Release-readiness report | Final report per master prompt §29. | – | Repeatable delivery | Medium | Must | P8 | Docs | – | – | LS-121, LS-122, LS-123, LS-126, LS-047 | Blocks: – Blocked by: LS-121, LS-122, LS-123, LS-126, LS-047 | 1. Verified vs assumed separated 2. Owner decision on release | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Review |  | 2 | Low | Low | Release & Deployment Coordinator | After deps | Low | feature/LS-133-release-readiness-report |  |  | To Do | Project owner (human) | Awaiting Approval B |  | None | N/A
LS-140 | Task | LS-EPIC-13 | Proposed future API contracts (incl. language negotiation) | docs/api/future-api-contracts.md marked PROPOSED – NOT IMPLEMENTED; locale parameter / Accept-Language and fallback. | – | Future-proofing | Low | Should | P8 | Docs | – | – | LS-037 | Blocks: – Blocked by: LS-037 | 1. Endpoints, errors, pagination, auth, versioning documented | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Review |  | 3 | Medium | Low | API & Backend Integration Architect | Yes | Low | feature/LS-140-proposed-future-api-contracts-incl |  |  | To Do | Project owner (human) | Awaiting Approval B |  | None | N/A
LS-141 | Task | LS-EPIC-13 | AI generation flow & multilingual child-safety plan | docs/api/ai-generation-flow.md: job-based flow, moderation in EN and KN, rate limits, retention, consent. | – | Future-proofing | Low | Should | P8 | Docs | – | – | LS-082 | Blocks: – Blocked by: LS-082 | 1. Safety controls defined per language | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Review |  | 3 | Medium | Low | AI Story Generation Integration Architect | Yes | Low | feature/LS-141-ai-generation-flow-multilingual-child |  |  | To Do | Project owner (human) | Awaiting Approval B |  | None | N/A
LS-150 | Task | LS-EPIC-15 | Configuration docs & 'How to change X' guide | docs/architecture/configuration-and-constants.md and how-to-change.md (colour, string, spacing, mock story, feature flag, language, screen). | – | Cheap future changes | Medium | Must | P2 | Docs | – | – | LS-033, LS-010, LS-040 | Blocks: – Blocked by: LS-033, LS-010, LS-040 | 1. Every central config point documented with file path | Std DoD: AC met · no hardcoded strings/colours/dims/config · EN + KN strings present · unit/UI tests pass · lint + translation check pass · screenshots EN/KN attached (UI) · docs updated · human PR review & merge · post-merge verified | Use tokens, string resources (EN+KN) and AppConfig only. | Doc walkthrough |  | 2 | Low | Low | Code Quality & Maintainability Reviewer | Yes | Low | claude/project-thread-veobz7 |  |  | In Review | Project owner (human) | Approval B granted — awaiting owner review of docs PR | Drafted 29 Oct 2026: docs/architecture/configuration-and-constants.md, how-to-change.md (drafted early in P1) | None | N/A |  | NFR-01
LS-009 | Task | LS-EPIC-12 | Repository hygiene: default branch main, development branch | Owner merges PR #1, sets the GitHub default branch back to main and creates development from main (decision D2, R-22). | – | Every branch and PR starts from the right base | Highest | Must | P1 | GitHub settings | – | – | LS-001 | Blocks: LS-030, LS-131 Blocked by: LS-001 | 1. Default branch is main 2. development exists from main 3. PR #1 merged by owner | Owner confirms settings changed | Owner action in GitHub settings; agents must not change repository settings. | Verify via GitHub API |  | 1 | Low | Medium | Release and Deployment Coordinator | Yes | Low | – |  |  | To Do | Project owner (human) | Awaiting owner (D2) |  | None | N/A
LS-039 | Task | LS-EPIC-12 | Build verification environment (ADR-017) | Make Android builds verifiable for agent PRs: allow dl.google.com in the cloud environment network settings and rely on GitHub Actions (LS-130) as the shared runner (decision D3, R-21). | – | PRs carry real build and test evidence | Highest | Must | P2 | Environment / CI | – | – | LS-009 | Blocks: LS-030, LS-035, LS-130 Blocked by: LS-009 | 1. A Gradle sync that downloads AGP succeeds in the agent workspace or CI 2. Decision recorded in ADR-017 | ADR-017 approved and verified with a real sync | Owner changes Network access in the project cloud environment; no credentials in the repo. | Gradle sync / assembleDebug run |  | 1 | Low | High | Build, Gradle & CI/CD Engineer | Yes | Low | – |  |  | To Do | Project owner (human) | Awaiting owner (D3) |  | None | N/A
Note on T1: Editable column – update as work progresses.
Note on AB1: Editable column – update as work progresses.
Note on AC1: Editable column – update as work progresses.
Note on AD1: Editable column – update as work progresses.
Note on AG1: Editable column – update as work progresses.
Note on AI1: Editable column – update as work progresses.
Note on AL1: Helper for the Board sheet: Status¦running count. Do not edit.

## Epics
Epic ID | Epic Name | Goal | Phases | Business Value | Tickets | Story Points | Done | % Done (points)
LS-EPIC-01 | Product Discovery and Requirements | Verified repo/design inventory, requirements, decisions, agent instructions | P0–P1 | Delivery clarity – avoids rework
LS-EPIC-02 | Design System (from Figma Make) | Tokens, typography, icons, reusable Compose components matching the design pack | P2 | Visual fidelity and consistency
LS-EPIC-03 | Android Foundation | Build, modules, DI, config, mock data, domain, persistence, tooling | P2 | Maintainable, testable base
LS-EPIC-04 | Navigation and Application Shell | Typed navigation for all screens, splash, system bars | P3 | Coherent app structure
LS-EPIC-05 | Onboarding and Profiles | Onboarding, child setup, multiple child profiles | P3–P6 | Personalised first-run experience
LS-EPIC-06 | Home and Story Discovery | Home, Discover, Category, Story Detail, favourites | P4 | Core browsing value
LS-EPIC-07 | Story Creation | Create form, simulated generation, story ready | P4 | Signature feature
LS-EPIC-08 | Reader and Audio | Reader, simulated player, sleep timer, progress | P5 | Bedtime reading/listening
LS-EPIC-09 | Saved Library and Downloads | My Stories, recently played, simulated downloads | P5–P6 | Re-engagement
LS-EPIC-10 | Parent Controls, Settings and Privacy | Settings hub, reminders, notifications, demo subscription, privacy, help | P6 | Parent trust and control
LS-EPIC-11 | Testing and Visual Quality | Unit/UI/E2E/screenshot/a11y/security reviews | P7 | Release confidence
LS-EPIC-12 | CI/CD and Release Readiness | Branching, CI, release docs | P1–P8 | Repeatable delivery
LS-EPIC-13 | Future Backend Integration Planning | Proposed API contracts, AI generation & safety plan | P8 | Future-proofing
LS-EPIC-14 | Localization (English, Kannada) and Future Languages | EN/KN everywhere, registry-driven languages, CI checks, native review | P2–P8 | Reach Kannada-speaking families
LS-EPIC-15 | Maintainability and Configuration | No hardcoding, central config, how-to-change docs | P2–P8 | Cheap future changes

## Roadmap
Phase | Name | Goal | Key Deliverables | Entry Criteria | Exit Criteria | Approval Gate | Tickets | Story Points | Done
P0 | Discovery | Read-only repo, toolchain and design audit | Discovery report; design inventory (done from design pack) | Session start | Report delivered | Approval A
P1 | Requirements & planning | Requirements, ADRs, backlog, prompts, agent instructions | docs/, backlog workbook, prompts/, CLAUDE.md, copilot-instructions.md | Approval A | Docs approved | Approval B
P2 | Foundation, design system & localization foundation | Build, modules, tokens, components, l10n infra, mock data, CI | Buildable app shell with tokens, components, EN/KN infra | Approval C | Build + tests + lint green | Approval C per ticket
P3 | App shell, navigation & onboarding | Nav graph, splash, onboarding, setup, profiles persistence | First-run journey A working EN/KN | P2 merged | Journey A verified | PR review
P4 | Home, discovery & creation | Home, Discover, Category, Detail, Create, Generating, Ready | Journeys B & C working | P3 merged | Journeys B, C verified | PR review
P5 | Reader, player & library | Reader, simulated player, sleep timer, My Stories, progress | Journeys D & F working | P4 contracts merged | Journeys D, F verified | PR review
P6 | Parent & supporting screens | Settings hub, profiles, reminders, notifications, downloads, subscription, language prefs, privacy, help | Journeys E & G working | P3 merged | Journeys E, G verified | PR review
P7 | Quality hardening | E2E, screenshots EN/KN, a11y, security, maintainability, native Kannada review | Evidence pack; defects fixed | P3–P6 merged | All Must tests pass | PR review
P8 | Release readiness | CI stable, release docs, backend plan, readiness report | Release-readiness report | P7 done | Owner sign-off | Approval F

## Screens
Design Preview | Screen ID | Screen Name | Figma Source (Make screen) | Screenshot File(s) | Design Details | Main Entry Point | Exit Paths | Components | States | Data Requirements | Accessibility Notes | Localization Notes | Screenshot Test Required | Related Ticket Keys | Design Status | Implementation Status | Review Status | Open Questions
| SCR-01 | Onboarding (3 slides) | Figma Make · Mobile App UI Prototype · screen 'onboarding' | 01-onboarding-1-every-day-has-a-story.jpg 02-onboarding-2-your-child-the-hero.jpg 03-onboarding-3-listen-dream-repeat.jpg | Night canvas #17152F. Sheet: eyebrow 'LITTLE STORIES. BIG IMAGINATION.' → title 29/1.12 Manrope → body 15/1.55 muted → pager (active dot 24px, others 7px) → button. Slide 1 'Every Day Has a Story'; 2 'Your Child, the Hero'; 3 'Listen, Dream, Repeat' (button 'Get Started'). Scene identical on all slides. No swipe and no back control in prototype. | First launch | Setup (Continue on slide 3 / Get Started / Skip) | Brand mark (light), Skip text button, night scene illustration (moon, clouds, twinkling stars, child reading), cream bottom sheet 32dp top radius, eyebrow, title, body, pager dots, primary button | Slide 1, Slide 2, Slide 3 | Static copy only | Pager must announce 'slide n of 3'; twinkle animation must respect reduced motion; Skip ≥48dp | 3 titles/bodies; body min-height 70px may grow in Kannada | EN + KN | LS-014, LS-060 | Design Ready | Not started | Not reviewed | Should slides support swipe and back? (not in prototype)
| SCR-02 | Setup – Child profile | Figma Make · Mobile App UI Prototype · screen 'setup' | 04-setup-profile.jpg | Badge 'Private & parent-managed' (green). Title 'Let’s make stories feel like home.' Fields: Parent name (Meera), Child’s name (Aarav), avatar row (3 faces + dashed +), Age 3–12 (6), Language (English), interests Animals/Cricket/Adventure/Space/Nature/Music (3 preselected, 'Optional'), duration 5/10/15 min (10). CTA 'Create {child}’s profile'. | Onboarding; Child Profiles (Add/Edit); Profile → Account settings | Home (CTA or 'Skip for now') | TopBar with brand + 'Skip for now', trust badge, form card (text fields, avatar picker, age select, language select, interest chips multi-select, segmented duration), sticky CTA | Default, editing, validation (name required – decision), saving | ChildProfile (parent name, child name, avatar, age 3–12, language, interests, default duration) | Labels bound to fields; chips expose selected state; select fields operable by TalkBack | Language list must come from SupportedLanguage registry (EN, ಕನ್ನಡ) – design shows 7 languages | EN + KN | LS-016, LS-045, LS-061, LS-062 | Design Ready | Not started | Not reviewed | Is parent name needed (data minimisation)? Required-field rules? Avatar '+' behaviour?
| SCR-03 | Home | Figma Make · Mobile App UI Prototype · screen 'home' | 05-home.jpg | Header 'Good evening' 12sp muted / 'Stories for Aarav' 21sp. Hero #35256F radius 26: kicker 'TONIGHT’S ADVENTURE', 'Tonight, anything is possible.', body, '+ Create a Story'. Continue card: '8 MIN · 42% COMPLETE', progress lavender, 'Resume story'. Categories: Bedtime, Animals, Adventure, Friendship, Indian Tales (pastel tiles). Culture banner #F5DFC0 'ROOTED IN WONDER / Stories from every corner of India'. | Setup; bottom nav | Notifications, Child Profiles, Create, Player, Discover, Category, Story Detail | Greeting header + bell + avatar, indigo hero card with illustration and white button, SectionHeader, ContinueCard, category tiles row, StoryCard row with heart toggle, culture banner, BottomNav | Populated; no continue-listening item (decision); empty 'Made for' (decision) | Active child, recently played + progress, categories, recommended stories, favourites | Hero image decorative; story cards announce title, category, duration, favourite state | 'Stories for {child}', 'Made for {child}' – name inside string must use format args | EN + KN | LS-014, LS-018, LS-070, LS-091 | Design Ready | Not started | Not reviewed | Greeting only shows 'Good evening' – time-of-day logic? Empty states for new user not designed
| SCR-04a | Discover | Figma Make · Mobile App UI Prototype · screen 'discover' | 06-discover.jpg | Search placeholder 'Search stories, themes, or characters'. Featured #242044: 'FEATURED THIS WEEK', 'The Little Elephant Who Shared', 'Listen now ▷'. Chips: All, Animals, Adventure, Friendship, Kindness, Nature, Space, Science, Panchatantra, Indian Folk Tales, Festivals, Learning. Sections 'Popular right now' (+View all) and 'Bedtime favourites'. | Bottom nav; Home 'See all' | Story Detail, Category, Notifications | TopBar brand+title+bell, search field with clear, dark featured card, horizontal filter chips, 2-column grid, horizontal row | Default, searching (featured hidden, title 'Results for …'), filtered by chip | Catalog, categories, favourites | Search field labelled; chip selection announced | Search must work for Kannada titles (locale-aware lowercase/contains) | EN + KN | LS-014, LS-016, LS-018, LS-071 | Design Ready | Not started | Not reviewed | Featured card 'Listen now' goes to Detail in prototype – should it open Player?
| SCR-04b | Discover – No results (empty state) | Figma Make · Mobile App UI Prototype · screen 'discover (empty)' | 06-discover.jpg | 'No stories found' / 'Try a different title or explore one of our story collections.' / 'Clear search' (resets query and chip to All). Described in design spec; not separately captured as screenshot. | Search with no match | Clear search → Discover default | Empty state (icon tile, title, body, secondary button) | Empty | None | Empty state title announced as heading | – | EN + KN | LS-017, LS-072 | Design Ready (spec only) | Not started | Not reviewed | No separate screenshot – confirm visual
| SCR-05 | Category (Indian Tales) | Figma Make · Mobile App UI Prototype · screen 'category' | 21-category-indian-tales.jpg | Hero 220px indigo: '18 STORIES', 'Indian Tales', description. 'Stories for curious minds' + sort pill. Rows: art 78×91, eyebrow category, title, 'Ages 4–7 · 6 min', green 'Available offline', heart. | Home category tile / culture banner; Discover 'View all' | Story Detail; back → Discover | TopBar with back + title, indigo category hero with arch illustration, sort select, ListStoryRow with heart | Populated; sort Recommended/Shortest first/Newest | Category, stories in category, downloaded flag, favourites | Sort control labelled; rows announce offline availability | '{n} stories' needs plurals | EN + KN | LS-018, LS-073 | Design Ready | Not started | Not reviewed | Prototype hard-codes Indian Tales – generic per category? Hero art per category?
| SCR-06 | Story Detail | Figma Make · Mobile App UI Prototype · screen 'detail' | 22-story-detail.jpg | Cover 355px. Pill category, title 27sp, metadata Ages 4–7 · 6 min · EN, synopsis 14/1.65, lesson panel #FFF4E8 with peach tile, 'Narrated story – Warm, expressive voice · English – ✓ Available'. Sticky: 'Listen to Story' (primary) + 'Read Story' (secondary). | Story cards/rows anywhere | Player (Listen), Reader (Read), back | Full-bleed cover with floating back/favourite/download, white body sheet, pill, metadata row, synopsis, 'A little lesson' panel, narration row, sticky dual CTA | Favourite on/off, downloaded on/off | Story (title, category, ages, minutes, language, synopsis, lesson, narration) | Cover decorative; metadata read as one phrase | Language tag 'EN' must reflect story language (EN/ಕನ್ನಡ) | EN + KN | LS-018, LS-044, LS-074 | Design Ready | Not started | Not reviewed | –
| SCR-07 | Create a Story | Figma Make · Mobile App UI Prototype · screen 'create' | 07-create-story.jpg 08-create-story-more-options-and-error.jpg | Textarea label 'What happened today?', counter n/500. Suggestions: A day at school, A family adventure, Something funny happened, I learned something new, An act of kindness. Hero select (Aarav, Ananya). Themes: Adventure*, Bedtime, Animals, Friendship, Fantasy, Learning, Indian folklore. More options: Mood Calm/Funny/Magical*/Adventurous; Duration 5/8*/10/15 minutes; Story language. Error 'Tell us one little moment to begin the story.' CTA 'Create My Story ✦'. | Home hero CTA; bottom nav Create | Generating (valid submit) | TopBar title + 'Parent guided' label, intro orb, textarea with counter, suggestion chips, story-hero selector, theme chips, collapsible 'More options' (mood, duration, story language), safety note, primary CTA, error banner | Default, more options expanded, validation error, typing clears error | Child profiles, StoryCreationRequest | Error must be announced (live region); counter readable; chips single-select semantics | Placeholder is gendered ('helped his friend') – needs neutral, translatable copy; counter uses format args | EN + KN | LS-016, LS-080, LS-081 | Design Ready | Not started | Not reviewed | Story language list must be EN/KN only; gendered placeholder copy
| SCR-08 | Generating + Paused | Figma Make · Mobile App UI Prototype · screen 'generating' | 09-generating.jpg | Eyebrow 'A STORY FOR AARAV', 'Creating your little adventure…', 'We’re weaving today’s moments into something wonderful.' Bar lavender→yellow. Stages: Imagining the adventure / Writing the story / Preparing the narration. Footnote 'This usually takes less than a minute.' Paused: 'Story creation paused', 'Your idea is still here. Continue whenever you’re ready.', Try again / Back to your idea. Prototype: +4% every 120ms. | Create submit | Story Ready (auto at 100%); Paused → Try again / Back to your idea | Night gradient, close button, twinkling stars, magic book, eyebrow, title, gradient progress bar + %, 3-stage list, footnote; paused state with icon + 2 buttons | Progress (stages <38% / <76% / ≥76%), paused (cancelled) | Simulated generation job | Progress announced politely (not every tick); close button labelled; reduced motion | 'A story for {CHILD}' uppercase via style, not string | EN + KN | LS-017, LS-082, LS-083 | Design Ready | Not started | Not reviewed | Paused state not captured as screenshot
| SCR-09 | Story Ready | Figma Make · Mobile App UI Prototype · screen 'generated' | 10-story-ready.jpg | Ribbon #E9F6EE '✓ Your story is ready'. Cover 385px, badge 'Made for Aarav'. 'A MAGICAL ADVENTURE', title 28sp, English · 8 min · Ages 5–9. 'A little peek inside' quote with lavender rule. Listen Now / Read Story. Row 'Saved to My Stories – Find it anytime in Created by Me'. | Generating complete; notification | Player, Reader, My Stories (Created by Me) | Success ribbon, cover with back/favourite/download + 'Made for' badge, body sheet, eyebrow, title, metadata, synopsis, pull-quote, dual buttons, 'Saved to My Stories' row | Ready | Generated story | Ribbon announced on arrival | Story content must be in selected story language | EN + KN | LS-018, LS-044, LS-082, LS-084 | Design Ready | Not started | Not reviewed | –
| SCR-10 | Reader | Figma Make · Mobile App UI Prototype · screen 'reader' | 11-reader.jpg | Background #FFFAF2. '1 of 5'. Paragraph Manrope 16/1.95 #393348, scalable in 0.1 steps. Reader nav: ghost Previous, round indigo play 54px, ghost Next. | Detail 'Read Story', Story Ready, Player 'Story text' | Player (narration button), back | TopBar 'Reading' + back + favourite, page indicator, A−/A+ buttons, 3dp reading progress, title, cover (page 1), paragraph, flourish, bottom bar Previous / play / Next | Page 1..n, first (Previous disabled), last (Next disabled), text scale 0.9–1.3 | Story pages, reading progress, text-size preference | A−/A+ labelled 'Decrease/Increase text size'; text must also respect system font scale | Kannada paragraphs need larger line height; page indicator uses format args | EN + KN | LS-018, LS-044, LS-090, LS-091 | Design Ready | Not started | Not reviewed | Persist text size per child or app-wide?
| SCR-11a | Player | Figma Make · Mobile App UI Prototype · screen 'player' | 12-player.jpg | Label 'NOW PLAYING FOR AARAV', cover 245×264 (265×290 tall phones), 'English · Narrated by Kavya', seek starts 31% (2:28/8:00), play 67px lavender. Secondary: Sleep timer, Download→Downloaded, Favourite→Loved, Speed cycles 0.75/1/1.25/1.5×. Volume default 75. | Detail 'Listen', Story Ready, Home continue card, Reader play | Reader ('Story text'), back | Night gradient, stars, back, 'Story text' link, label, cover with glow, title, narrator line, seek slider + times, 5 transport controls, 4 secondary controls, volume slider | Paused/playing, downloaded, favourite, speed 0.75–1.5×, timer set | Simulated playback state | All controls labelled; slider exposes value; 15s glyphs overlap (defect) | 'Narrated by {name}', 'Now playing for {child}' via format args | EN + KN | LS-018, LS-091, LS-092, LS-094 | Design Ready | Not started | Not reviewed | Simulated audio must be labelled as simulation – where? 15s glyph overlap
| SCR-11b | Player – Sleep timer sheet | Figma Make · Mobile App UI Prototype · screen 'player (sleep sheet)' | 13-player-sleep-timer-sheet.jpg | 'Sleep timer', 'Audio will gently stop when the timer ends.' Options: 10 minutes, 15 minutes, 30 minutes, End of story. Selected label replaces 'Sleep timer' on button. | Player 'Sleep timer' | Player (select or Cancel / tap outside) | Modal bottom sheet with handle, title, body, 4 option rows with check, Cancel ghost button, dim overlay | None selected / option selected | Sleep timer value | Sheet focus trapped; selected option announced | – | EN + KN | LS-017, LS-093 | Design Ready | Not started | Not reviewed | –
| SCR-12 | My Stories | Figma Make · Mobile App UI Prototype · screen 'library' | 14-my-stories.jpg | Tabs: All, Created by Me, Downloaded, Favourites. All tab: 'Recently played' card ('3:24 remaining'), 'Your collection'. Empty Downloaded: 'Ready for offline adventures?'; others 'No stories here yet' – both 'Discover stories'. | Bottom nav; Story Ready row | Player, Story Detail, Story Ready (created), Offline Downloads, Discover | TopBar brand+title+download icon, search, pill tabs, recently played card, list rows with play, empty states | All, Created by Me, Downloaded, Favourites, empty (Downloaded / others), searching | Saved/created/downloaded/favourite stories, recently played | Tabs expose selected state | Tab labels may wrap in Kannada – horizontal scroll | EN + KN | LS-014, LS-016, LS-017, LS-018, LS-091, LS-100 | Design Ready | Not started | Not reviewed | –
| SCR-13 | Profile (settings hub) | Figma Make · Mobile App UI Prototype · screen 'settings' | 15-profile-settings.jpg | Parent card: Meera Sharma, meera@example.com, 'Account settings'. CHILDREN: Manage children, Language preferences. EXPERIENCE: Bedtime reminders (toggle), Notifications (toggle), Audio preferences, Download settings (Wi-Fi only toggle). LITTLESTORY: Subscription (Free plan), Privacy & parent controls, Help & about (Version 1.0 prototype). Screenshot still shows old 'LittleKatha' brand. | Bottom nav Profile | Setup, Child Profiles, Language prefs, Reminders, Notifications, Audio prefs, Downloads, Subscription, Privacy, Help | Indigo parent card, grouped settings rows with icon tiles, toggles, chevrons, footer brand | Toggles on/off | Parent info, children, settings | Prototype nests a toggle inside a row button – must be separate targets | Group headings uppercase via style; 'Every day at {time}' locale time format | EN + KN | LS-014, LS-016, LS-046, LS-110 | Design Ready | Not started | Not reviewed | Several rows route to placeholder screens in prototype (Audio → Player, Privacy/Help → Notifications, Language → Setup)
| SCR-14 | Child Profiles | Figma Make · Mobile App UI Prototype · screen 'profiles' | 20-child-profiles.jpg | Privacy note 'Private family profiles – Only you can see and manage your children’s details.' Cards: Aarav (6 · English · Animals · Cricket · Adventure, ✓ Active), Ananya (9 · Hindi · Space · Science · Music, Switch). 'Add another child – Personalise stories for every little listener'. | Home avatar; Profile → Manage children | Setup (add/edit), back → Profile | TopBar title + 'Add child', privacy note, profile cards (active pill / Switch, edit pencil), dashed add row | Active/inactive profiles | ChildProfile list, active profile | Edit icon labelled per child; active state announced | '{age} years · {language}' via plurals/format | EN + KN | LS-062, LS-063 | Design Ready | Not started | Not reviewed | Delete profile not designed; max profiles?
| SCR-15 | Subscription (demo) + dialog | Figma Make · Mobile App UI Prototype · screen 'subscription' | 16-subscription.jpg | Plans: Free ₹0 'Try the magic', Premium Monthly ₹249, Premium Yearly ₹1,799 'best value' (preselected), Premium Family ₹2,499 'up to 5 children'. 'Illustrative pricing only. No real payment will be processed.' CTA 'Choose {plan} Plan'. Dialog 'Plan selected – This is a prototype, so no payment was made…'. Screenshot shows old 'LITTLEKATHA PREMIUM'. | Profile → Subscription | Home (Done), back | Night hero with moon, eyebrow, title, body, 2-col benefits checklist, plan radio list with BEST VALUE tag, disclaimer, CTA, legal links, confirmation dialog | Plan selected (Yearly default), confirmation dialog | Demo plans (feature-flagged) | Radio group semantics; dialog focus | Prices must use locale currency formatting (₹) | EN + KN | LS-017, LS-113 | Design Ready | Not started | Not reviewed | Ship demo subscription in MVP or hide behind flag?
| SCR-16 | Bedtime Reminder | Figma Make · Mobile App UI Prototype · screen 'reminders' | 17-bedtime-reminder.jpg | Panel 'A gentle nudge for storytime', 'We’ll keep it quiet and calm—just one reminder.' Toggle 'Bedtime reminder – Pause anytime', time 20:30, days M T W T F S S all on, 'Quiet bedtime experience – No sound, no bright alerts'. CTA 'Save reminder' → toast 'Reminder saved for {time}'. | Profile → Bedtime reminders; notification | Back → Profile | Indigo visual panel, setting card: toggle, time input, 7 day buttons, quiet row, primary CTA, toast | Enabled/disabled (time & days disabled), saved toast | Reminder settings (local) | Day buttons need full day names for TalkBack; toggle labelled | Day initials and time format are locale-specific (use DayOfWeek/DateTimeFormatter) | EN + KN | LS-016, LS-017, LS-111 | Design Ready | Not started | Not reviewed | Actually schedule a local notification in MVP? (needs POST_NOTIFICATIONS)
| SCR-17 | Offline Downloads | Figma Make · Mobile App UI Prototype · screen 'downloads' | 18-offline-downloads.jpg | Storage card '{n} MB used / of 1 GB available for stories', yellow bar (min 3%). Rows '✓ AVAILABLE OFFLINE', title, '{size} MB · Audio & story', ✕. Empty 'No downloads yet' → 'Find a story'. Tip 'Offline means worry-free…'. | My Stories download icon; Profile → Download settings | Discover (empty CTA), back | Indigo storage card with bar, downloaded list rows with remove ✕, empty state, green tip | Has downloads, empty | Downloaded stories (simulated) and sizes | Remove button labelled with story title | '{n} MB used' number formatting | EN + KN | LS-017, LS-018, LS-101 | Design Ready | Not started | Not reviewed | Downloads are simulated in MVP – label accordingly
| SCR-18 | Notifications | Figma Make · Mobile App UI Prototype · screen 'notifications' | 19-notifications.jpg | 'Mark all read'. TODAY: 'Your new story is ready' (unread), 'Storytime is at 8:30 PM'. EARLIER: 'Fresh tales from India'. Icon tiles lavender/peach/yellow. | Home/Discover bell; Profile → Notifications | Story Ready, Reminders, Discover | TopBar title + 'Mark all read', section labels, notification rows with tinted icon tiles and unread dot | Unread/read, empty (not designed) | Mock notifications | Unread state announced, not colour only | Notification text is mock content (per-language JSON) | EN + KN | LS-112 | Design Ready | Not started | Not reviewed | Empty state not designed
No design yet | SCR-19 | Splash / launch | Not in Figma Make file | – (no design) | NOT IN DESIGN. Propose: cream or night background with LittleStory symbol via core-splashscreen. | App start | Onboarding (first run) or Home | Android 12+ SplashScreen API (icon + background) | – | First-run flag | – | – | After design | LS-051 | Design Missing | Not started | Not reviewed | Need splash spec + app icon
No design yet | SCR-20 | Language preferences | Not in Figma Make file | – (no design) | NOT IN DESIGN. Prototype routes to Setup. Propose a simple list screen reusing settings rows: English / ಕನ್ನಡ with check. | Profile → Language preferences | Back → Profile | Language list (registry-driven), selection state | Selected | App language, default story language | Each language shown in own script | Core of EN/KN requirement | After design | LS-046 | Design Missing | Not started | Not reviewed | App language vs story language – one setting or two?
No design yet | SCR-21 | Privacy & parent controls | Not in Figma Make file | – (no design) | NOT IN DESIGN. Prototype routes to Notifications. | Profile → Privacy & parent controls | Back → Profile | Info sections, data deletion action (local), parental gate? | – | Local data summary | – | Long text – must wrap in Kannada | After design | LS-114 | Design Missing | Not started | Not reviewed | Content and controls to be defined (data delete, parental gate)
No design yet | SCR-22 | Help & about | Not in Figma Make file | – (no design) | NOT IN DESIGN. Prototype routes to Notifications. | Profile → Help & about | Back → Profile | App version, licences (fonts OFL), help text | – | BuildConfig version | – | – | After design | LS-115 | Design Missing | Not started | Not reviewed | Content to be defined
No design yet | SCR-23 | Account settings / Audio preferences | Not in Figma Make file | – (no design) | NOT IN DESIGN. Prototype routes 'Account settings' → Setup and 'Audio preferences' → Player. | Profile parent card; Profile → Audio preferences | Back | – | – | – | – | – | After design | – | Design Missing | Not started | Not reviewed | Needed for MVP or remove rows?

## Design Gallery
Design Gallery
Full-length captures from the Figma Make prototype (430 px frame). Pre-rename: logo and Premium banner still say 'LittleKatha' – build uses 'LittleStory'.
| SCR-01 · Onboarding (3 slides) | SCR-01 · Onboarding (3 slides) | SCR-01 · Onboarding (3 slides) | SCR-02 · Setup – Child profile
| 01-onboarding-1-every-day-has-a-story.jpg | 02-onboarding-2-your-child-the-hero.jpg | 03-onboarding-3-listen-dream-repeat.jpg | 04-setup-profile.jpg
| SCR-03 · Home | SCR-04a · Discover | SCR-05 · Category (Indian Tales) | SCR-06 · Story Detail
| 05-home.jpg | 06-discover.jpg | 21-category-indian-tales.jpg | 22-story-detail.jpg
| SCR-07 · Create a Story | SCR-07 · Create a Story | SCR-08 · Generating + Paused | SCR-09 · Story Ready
| 07-create-story.jpg | 08-create-story-more-options-and-error.jpg | 09-generating.jpg | 10-story-ready.jpg
| SCR-10 · Reader | SCR-11a · Player | SCR-11b · Player – Sleep timer sheet | SCR-12 · My Stories
| 11-reader.jpg | 12-player.jpg | 13-player-sleep-timer-sheet.jpg | 14-my-stories.jpg
| SCR-13 · Profile (settings hub) | SCR-14 · Child Profiles | SCR-15 · Subscription (demo) + dialog | SCR-16 · Bedtime Reminder
| 15-profile-settings.jpg | 20-child-profiles.jpg | 16-subscription.jpg | 17-bedtime-reminder.jpg
| SCR-17 · Offline Downloads | SCR-18 · Notifications
| 18-offline-downloads.jpg | 19-notifications.jpg

## Design System
Design System Tokens
From design-tokens.json / LittleStory_Figma_Design_Details.md. Proposed Compose token names – the only place these values may appear in code.
Group | Token | Value | Used for | Proposed Compose token | Swatch
Colour | indigo | #35256F | Primary buttons, hero, active nav, links | LsColors.primary
Colour | indigo-2 | #4B388B | Eyebrow labels | LsColors.eyebrow
Colour | lavender | #A995F5 | Focus ring, progress, selected outline | LsColors.accent
Colour | soft-lavender | #EAE3FF | Secondary button, selected chip, nav pill, icon tiles | LsColors.accentContainer
Colour | night | #17152F | Dark canvas (onboarding, generating, player, premium) | LsColors.night
Colour | night-surface | #242044 | Dark raised surface (featured card) | LsColors.nightSurface
Colour | cream | #FFF9F0 | App background | LsColors.background
Colour | white | #FFFFFF | Cards, inputs | LsColors.surface
Colour | surface | #F8F5FB | Segmented track | LsColors.surfaceVariant
Colour | line | #E9E4EC | Borders, dividers | LsColors.outline
Colour | yellow | #FFD977 | Stars, moon, kickers on dark | LsColors.star
Colour | peach | #FFC9AD | Lesson tile | LsColors.peach
Colour | moon | #FFF1BD | Crescent moon | LsColors.moon
Colour | text | #25213A | Primary text | LsColors.onBackground
Colour | muted | #716B80 | Secondary text (check contrast) | LsColors.textMuted
Colour | reader-body | #393348 | Story paragraphs | LsColors.readerText
Colour | nav-inactive | #817B8D | Inactive tab labels (check contrast) | LsColors.navInactive
Colour | success | #287A54 | Success, toggle on, step done | LsColors.success
Colour | success-bg | #EAF5EE | Trust/privacy notes | LsColors.successContainer
Colour | error | #B42318 | Form error | LsColors.error
Colour | favourite | #9D3158 | Active heart | LsColors.favourite
Colour | favourite-bg | #FFEDF2 | Active heart background | LsColors.favouriteContainer
Story art | friendship | #F6B995 → #694B91 | Gradient 145° | StoryPalette.Friendship
Story art | adventure | #6252A6 → #F2A978 | Gradient 145° | StoryPalette.Adventure
Story art | bedtime | #32306D → #9F91E9 | Gradient 145° | StoryPalette.Bedtime
Story art | indianTales | #47796B → #EFBB69 | Gradient 145° | StoryPalette.IndianTales
Story art | space | #25285D → #DB82A6 | Gradient 145° | StoryPalette.Space
Story art | festivals | #B15B54 → #F5C568 | Gradient 145° | StoryPalette.Festivals
Typography | Body family | DM Sans 400/500/600/700 | Body, buttons, labels | LsFonts.body
Typography | Display family | Manrope 500/600/700/800 | Headings, brand, top bar, reader paragraphs | LsFonts.display
Typography | Kannada fallback | Noto Sans Kannada (proposed) | Kannada glyphs (ADR-008) | LsFonts.kannada
Typography | onboarding-title | 29sp / 1.12, −0.8 tracking, Manrope | Onboarding title | LsType.displayLarge
Typography | setup-title | 29sp / 1.18, −0.8 | Setup title | LsType.displayMedium
Typography | hero-title | 25sp / 1.12, −0.7 (22sp compact) | Home hero | LsType.headlineLarge
Typography | home-title | 21sp, −0.5 | Home greeting | LsType.headlineMedium
Typography | topbar-title | 17sp, 800 | Top bar title | LsType.titleLarge
Typography | brand-name | 18sp, 800, −0.5 | Wordmark | LsType.brand
Typography | body-large | 15sp / 1.55 | Onboarding body | LsType.bodyLarge
Typography | reader-body | 16sp / 1.95, Manrope, scale 0.9–1.3 | Reader paragraph | LsType.reader
Typography | chip | 12sp, 600 | Chips | LsType.labelLarge
Typography | eyebrow | 10sp, 800, +1.6, uppercase | Eyebrows | LsType.eyebrow
Typography | hero-kicker | 9sp, 800, +1.4 | Hero kicker | LsType.kicker
Typography | nav-label | 10sp, 600 | Bottom nav labels | LsType.labelSmall
Shape | radius lg / md / sm | 24 / 18 / 13 | Cards, inputs | LsShapes.large/medium/small
Shape | button | 16 | Buttons (52dp min height) | LsShapes.button
Shape | hero | 26 | Home hero | LsShapes.hero
Shape | sheet | 32 top corners | Onboarding sheet, bottom sheets | LsShapes.sheet
Shape | chip | 20 (pill) | Chips, tabs | LsShapes.chip
Shape | avatar | 15 (large 19) | Avatar | LsShapes.avatar
Elevation | shadow | 0 12 30 #2318461C | Raised | LsElevation.raised
Elevation | shadow-soft | 0 5 18 #23184614 | Cards | LsElevation.soft
Elevation | primary-button | 0 8 18 #35256F33 | Primary button | LsElevation.button
Elevation | hero | 0 16 30 #35256F33 | Hero card | LsElevation.hero
Layout | topbar-height | 68dp | Top bar | LsDimens.topBarHeight
Layout | bottom-nav-height | 76dp + inset | Bottom nav | LsDimens.bottomNavHeight
Layout | content-padding | 6 / 20 / 28 (16 sides compact) | Page content | LsDimens.contentPadding
Layout | icon-button | 42dp visual / ≥48dp touch | Icon buttons | LsDimens.iconButton
Layout | breakpoints | ≤360dp compact; ≥900dp tall | Responsive | WindowSizeClass
Motion | twinkle | 2.4s / 1.7s / 1.1s alternate infinite | Stars (respect reduced motion) | LsMotion.twinkle*
Motion | button press | 180ms, scale .98 | Buttons | LsMotion.press
Motion | toggle / icon state / chevron | 200ms | Toggles, icon buttons, more options | LsMotion.short
Motion | reading progress | 300ms | Reader bar | LsMotion.medium
Components (design pack §2)
Component | Spec | Ticket
Button | primary / secondary / ghost, 52dp, radius 16, disabled 45% | LS-015
IconButton | 42dp circle, active favourite rose | LS-015
TopBar / BottomNav | 68dp bar; 5 tabs, raised Create tile | LS-019
SectionHeader | Manrope title + See all | LS-018
StoryCard / ListStoryRow / ContinueCard | Cover art + meta + heart/play | LS-018
Chips / Segmented / Toggle / Search / Tabs | Selected = soft-lavender | LS-016
Form card & inputs | 48dp inputs, radius 13, lavender focus | LS-016
Avatar | CSS-drawn face, selected outline | LS-018
Bottom sheet / Dialog / Toast / Empty state / Notes banner | See spec | LS-017
Progress bars | Reading, generation, playback, storage | LS-017
StoryArt illustration | Gradient + moon + stars + hill + motif | LS-018
Brand mark | LittleStory wordmark + symbol, light variant | LS-014

## Requirements
Req ID | Type | Title | Description | MoSCoW | Source | Related Screens | Tickets | Test Cases | Status
FR-01 | Functional | Onboarding | 3-slide intro with Skip, Continue and Get Started leading to Setup | Must | Design SCR-01 | SCR-01 | LS-060 | TC-001, TC-002 | Proposed – awaiting owner review
FR-02 | Functional | Child profile setup | Capture parent name, child name, avatar, age 3–12, language, optional interests and default duration | Must | Design SCR-02 | SCR-02 | LS-061, LS-062 | TC-004, TC-005 | Proposed – awaiting owner review
FR-03 | Functional | Multiple child profiles | List, switch active, edit and add child profiles | Should | Design SCR-14 | SCR-14 | LS-062, LS-063 | TC-042 | Proposed – awaiting owner review
FR-04 | Functional | Personalised Home | Greeting, hero CTA, continue listening, category tiles, 'Made for {child}' row, culture banner | Must | Design SCR-03 | SCR-03 | LS-070 | TC-008, TC-009, TC-010 | Proposed – awaiting owner review
FR-05 | Functional | Discover | Live search, featured story, category filter chips, popular grid, bedtime row, no-results state | Must | Design SCR-04a/b | SCR-04a, SCR-04b | LS-071, LS-072 | TC-011, TC-012, TC-013, TC-014 | Proposed – awaiting owner review
FR-06 | Functional | Category listing | Category hero and story list with sort (Recommended, Shortest first, Newest) | Should | Design SCR-05 | SCR-05 | LS-073 | TC-015 | Proposed – awaiting owner review
FR-07 | Functional | Story detail | Cover, favourite, download, metadata, synopsis, lesson, narration info, Listen/Read CTAs | Must | Design SCR-06 | SCR-06 | LS-074 | TC-016 | Proposed – awaiting owner review
FR-08 | Functional | Create story form | Text up to 500 chars, suggestions, hero, theme, more options (mood, duration, story language), empty-text validation | Must | Design SCR-07 | SCR-07 | LS-080, LS-081 | TC-019, TC-020, TC-021, TC-022, TC-061 | Proposed – awaiting owner review
FR-09 | Functional | Simulated generation | Deterministic progress with 3 stages, cancel → paused, try again, back to idea, auto-advance | Must | Design SCR-08 | SCR-08 | LS-082, LS-083 | TC-024, TC-025, TC-026, TC-027 | Proposed – awaiting owner review
FR-10 | Functional | Story ready | Result with listen/read and automatic save to 'Created by Me' | Must | Design SCR-09 | SCR-09 | LS-082, LS-084 | TC-028, TC-029 | Proposed – awaiting owner review
FR-11 | Functional | Reader | Paginated story, A−/A+ (0.9–1.3), reading progress bar, previous/next, play narration | Must | Design SCR-10 | SCR-10 | LS-090 | TC-030, TC-031 | Proposed – awaiting owner review
FR-12 | Functional | Simulated audio player | Play/pause, seek, ±15 s, chapters, speed 0.75–1.5×, volume, download, favourite, sleep timer – clearly simulated | Should | Design SCR-11a/b | SCR-11a, SCR-11b | LS-092, LS-093 | TC-034, TC-035, TC-037 | Proposed – awaiting owner review
FR-13 | Functional | Favourites | Toggle favourite from any story surface; state consistent and persisted | Must | Design (multiple) | SCR-03, SCR-04a, SCR-05, SCR-06, SCR-09, SCR-10, SCR-11a | LS-075 | TC-017, TC-018 | Proposed – awaiting owner review
FR-14 | Functional | My Stories library | Search, tabs (All, Created by Me, Downloaded, Favourites), recently played, empty states | Must | Design SCR-12 | SCR-12 | LS-100 | TC-038, TC-039 | Proposed – awaiting owner review
FR-15 | Functional | Offline downloads (simulated) | Storage summary, list, remove, empty state | Could | Design SCR-17 | SCR-17 | LS-101 | TC-040 | Proposed – awaiting owner review
FR-16 | Functional | Settings hub | Parent card and grouped settings rows with working toggles and navigation | Must | Design SCR-13 | SCR-13 | LS-110 | TC-041 | Proposed – awaiting owner review
FR-17 | Functional | Bedtime reminder settings | Enable, time, repeat days, save with toast (local only) | Could | Design SCR-16 | SCR-16 | LS-111 | TC-043, TC-044 | Proposed – awaiting owner review
FR-18 | Functional | Notifications inbox (mock) | Grouped mock notifications, unread markers, mark all read, deep links | Could | Design SCR-18 | SCR-18 | LS-112 | TC-045 | Proposed – awaiting owner review
FR-19 | Functional | Demo subscription | Plans with illustrative ₹ pricing, selection, confirmation dialog, no payment | Could | Design SCR-15 | SCR-15 | LS-113 | TC-046 | Proposed – awaiting owner review
FR-20 | Functional | App language EN / ಕನ್ನಡ | Select app language, apply app-wide, persist, English fallback | Must | Explicit instruction (owner) | SCR-02, SCR-20 | LS-004, LS-040, LS-045, LS-046 | TC-006, TC-007, TC-048, TC-049 | Proposed – awaiting owner review
FR-21 | Functional | Story language EN / ಕನ್ನಡ | Catalog and created stories available in English and Kannada | Must | Explicit instruction (owner) | SCR-06, SCR-07, SCR-09, SCR-10 | LS-036, LS-044, LS-081 | TC-023, TC-060 | Proposed – awaiting owner review
FR-22 | Functional | Privacy & parent controls | Explain data handling; allow deleting local data | Should | Design row exists; screen missing | SCR-21 | LS-004, LS-114 | – | Proposed – awaiting owner review
FR-23 | Functional | Help & about | Version, licences, help text | Could | Design row exists; screen missing | SCR-22 | LS-004, LS-115 | – | Proposed – awaiting owner review
FR-24 | Functional | Progress & resume | Reading and listening progress persisted; resume from Home/My Stories | Should | Design SCR-03, SCR-12 | SCR-03, SCR-10, SCR-11a, SCR-12 | LS-070, LS-091 | TC-033 | Proposed – awaiting owner review
FR-25 | Functional | Launch & first-run routing | Splash then onboarding on first run, Home afterwards | Must | Assumption (design missing) | SCR-19 | LS-004, LS-051 | TC-057 | Proposed – awaiting owner review
NFR-01 | Non-functional | No hardcoding | No hardcoded user-facing text, colours, dimensions, typography, routes, limits or config | Must | Explicit instruction (owner) | All | LS-005, LS-010, LS-011, LS-012, LS-033, LS-034, LS-050, LS-125, LS-150 | TC-051 | Proposed – awaiting owner review
NFR-02 | Non-functional | Localization completeness | Every string in EN and KN; CI key-parity check; lint MissingTranslation = error | Must | Explicit instruction (owner) | All | LS-005, LS-011, LS-034, LS-040, LS-041, LS-043, LS-047 | TC-003, TC-050 | Proposed – awaiting owner review
NFR-03 | Non-functional | Future languages | Adding a language = resources + registry + locales_config only | Must | Explicit instruction (owner) | All | LS-040, LS-042, LS-048 | TC-052, TC-059 | Proposed – awaiting owner review
NFR-04 | Non-functional | Accessibility | 48dp targets, WCAG AA contrast, TalkBack labels EN/KN, font scaling, reduced motion | Must | Master prompt §8.4 + design a11y gaps | All | LS-012, LS-015, LS-016, LS-017, LS-019, LS-094, LS-110, LS-123 | TC-032, TC-053, TC-054, TC-055 | Proposed – awaiting owner review
NFR-05 | Non-functional | Architecture | Clean layers, no circular deps, domain free of Android/UI | Must | Master prompt §9 | All | LS-008, LS-031, LS-037, LS-120 | – | Proposed – awaiting owner review
NFR-06 | Non-functional | Deterministic data | Stable IDs, per-language mock JSON, no random/timestamps in tests | Must | Master prompt §10 | All | LS-036 | – | Proposed – awaiting owner review
NFR-07 | Non-functional | Privacy & child safety | Minimal child data, no network/analytics/secrets in MVP | Must | Master prompt §8.5 | All | LS-038, LS-061, LS-114, LS-126 | TC-047 | Proposed – awaiting owner review
NFR-08 | Non-functional | Performance | No main-thread blocking, lazy lists, stable state | Should | Master prompt §8.2 | All | – | – | Proposed – awaiting owner review
NFR-09 | Non-functional | Cross-platform development | Builds identically on Windows and macOS; UTF-8; line endings normalised | Must | Explicit instruction (owner) | – | LS-001, LS-005, LS-030, LS-132 | TC-056 | Proposed – awaiting owner review
NFR-10 | Non-functional | Visual fidelity | Screens match the design pack screenshots to agreed tolerance | Must | Master prompt §16 | All | LS-002, LS-010, LS-013, LS-018, LS-020, LS-122, LS-124 | – | Proposed – awaiting owner review
NFR-11 | Non-functional | Reliability | State survives rotation, process recreation (where persisted) and language change | Must | Master prompt §8.3 | All | LS-038 | TC-058 | Proposed – awaiting owner review
NFR-12 | Non-functional | Honest simulations | Simulated generation, audio, downloads, subscription clearly labelled | Must | Master prompt §4.3 | SCR-08, SCR-11a, SCR-15, SCR-17 | LS-082, LS-092, LS-101, LS-113 | TC-036 | Proposed – awaiting owner review
NFR-13 | Non-functional | Locale-aware formatting | Numbers, dates, times, durations, weekdays and currency formatted with locale-aware APIs; no concatenation | Must | Brief §4.4 rule 12, §8.7 (NEW, proposed) | SCR-11a, SCR-15, SCR-16, SCR-17 | LS-040, LS-092, LS-101, LS-111, LS-113 | – | Proposed – awaiting owner review
NFR-14 | Non-functional | RTL and text-expansion readiness | supportsRtl, start/end only, flexible text containers; en-XA and ar-XB pseudo-locales render without clipping | Must | Brief §4.4 rules 10, 11, 18 (NEW, proposed) | All | LS-013, LS-016, LS-019, LS-042 | – | Proposed – awaiting owner review
NFR-15 | Non-functional | Configurability and How to change X | Every configurable value has one documented home; changing wording, colour, limit or mock story edits one file | Must | Brief §4.5, §8.8 (NEW, proposed) | All | LS-033, LS-125, LS-150 | – | Proposed – awaiting owner review
NFR-16 | Non-functional | Compatibility and device matrix | Supported Android versions (minSdk per ADR-016), screen sizes and test devices documented and tested | Must | Brief §8.6 (NEW, proposed) | All | LS-030, LS-132 | – | Proposed – awaiting owner review
NFR-17 | Non-functional | Build verifiability | Every PR carries build, test and lint evidence from CI or a documented local run; no unverified claims | Must | P0 finding R-21 (NEW, proposed) | – | LS-039, LS-130, LS-030 | – | Proposed – awaiting owner review

## Test Cases
Test Case ID | Related Ticket | Requirement ID | Screen | Locale | Scenario | Preconditions | Test Steps | Expected Result | Test Type | Automation Candidate | Priority | Test Data | Result | Evidence | Defect Link
TC-001 | LS-060 | FR-01 | SCR-01 | en | Advance through onboarding | Fresh install | Tap Continue ×2, then Get Started | Slides 1→2→3 copy matches design; Setup opens | UI | Yes | High | – | Not run
TC-002 | LS-060 | FR-01 | SCR-01 | en | Skip onboarding | Fresh install | Tap Skip on slide 1 | Setup opens | UI | Yes | Medium | – | Not run
TC-003 | LS-060 | NFR-02 | SCR-01 | kn | Onboarding in Kannada | App language ಕನ್ನಡ | View all 3 slides | All text Kannada, no clipping, button fits | Localization | Yes | High | – | Not run
TC-004 | LS-061 | FR-02 | SCR-02 | en | Create profile happy path | On Setup | Enter child name, pick avatar, age 6, interests, 10 min; tap CTA | Profile saved; Home shows 'Stories for {name}' | UI | Yes | High | Child 'Aarav' | Not run
TC-005 | LS-061 | FR-02 | SCR-02 | en | Required child name | On Setup | Clear child name; tap CTA | Validation per LS-004 decision; no navigation | UI | Yes | High | Empty name | Not run
TC-006 | LS-045 | FR-20 | SCR-02 | en | Language list from registry | On Setup | Open Language select | Only 'English' and 'ಕನ್ನಡ' shown | UI | Yes | High | – | Not run
TC-007 | LS-045 | FR-20 | SCR-02 | en→kn | Switch to Kannada in setup | On Setup | Choose ಕನ್ನಡ | UI switches to Kannada immediately; persists after restart | Integration | Yes | Highest | – | Not run
TC-008 | LS-070 | FR-04 | SCR-03 | en | Home populated | Profile + progress exist | Open Home | Hero, continue card (42%), categories, Made for row, banner present | Screenshot | Yes | High | Seed data | Not run
TC-009 | LS-070 | FR-04 | SCR-03 | en | Home with no progress | New profile | Open Home | Continue section hidden or empty state per decision | UI | Yes | Medium | – | Not run
TC-010 | LS-070 | FR-04 | SCR-03 | en | Home navigation | On Home | Tap bell, avatar, hero CTA, continue, tile, card, banner link | Each opens correct screen per spec | UI | Yes | High | – | Not run
TC-011 | LS-071 | FR-05 | SCR-04a | en | Live search | On Discover | Type 'moon' | Featured hidden; title 'Results for “moon”'; Mira and the Moonlit Garden shown | UI | Yes | High | Query 'moon' | Not run
TC-012 | LS-071 | FR-05 | SCR-04a | kn | Search Kannada title | Language ಕನ್ನಡ | Type part of a Kannada title | Matching story shown | Localization | Yes | High | KN query | Not run
TC-013 | LS-072 | FR-05 | SCR-04b | en | No results | On Discover | Type 'zzz'; tap Clear search | Empty state shown; clear restores All + featured | UI | Yes | Medium | 'zzz' | Not run
TC-014 | LS-071 | FR-05 | SCR-04a | en | Category chip filter | On Discover | Tap 'Space' | Only Space stories in grid | UI | Yes | Medium | – | Not run
TC-015 | LS-073 | FR-06 | SCR-05 | en | Sort shortest first | On Category | Select Shortest first | Rows ordered by minutes ascending | Unit | Yes | Medium | – | Not run
TC-016 | LS-074 | FR-07 | SCR-06 | en | Detail actions | On Detail | Tap Listen; back; tap Read | Player then Reader open | UI | Yes | High | Story 1 | Not run
TC-017 | LS-075 | FR-13 | Multiple | en | Favourite consistency | Story unfavourited | Favourite on Detail; open Home and My Stories ▸ Favourites | Heart active everywhere; listed in Favourites | Integration | Yes | High | Story 3 | Not run
TC-018 | LS-075 | FR-13 | Multiple | en | Favourite persistence | Story favourited | Kill and relaunch app | Still favourited | Integration | Yes | High | – | Not run
TC-019 | LS-081 | FR-08 | SCR-07 | en | Empty submission | On Create, empty text | Tap Create My Story | Error banner shown and announced; stays on Create | UI | Yes | Highest | – | Not run
TC-020 | LS-081 | FR-08 | SCR-07 | en | Error clears on typing | Error visible | Type a letter | Error disappears | UI | Yes | Medium | – | Not run
TC-021 | LS-080 | FR-08 | SCR-07 | en | Character limit | On Create | Paste 600 chars | Input capped at limit; counter shows 500/500 | Unit | Yes | High | 600-char text | Not run
TC-022 | LS-080 | FR-08 | SCR-07 | en | Suggestion fills text | On Create | Tap 'A day at school' | Textarea filled with sample sentence | UI | Yes | Low | – | Not run
TC-023 | LS-081 | FR-21 | SCR-07 | en | Story language options | More options open | Open Story language | Only English and ಕನ್ನಡ | UI | Yes | High | – | Not run
TC-024 | LS-082 | FR-09 | SCR-08 | en | Deterministic generation | Valid request | Generate twice with same input | Identical story output | Unit | Yes | High | Fixed request | Not run
TC-025 | LS-083 | FR-09 | SCR-08 | en | Stage progression | Generating | Advance test clock | Stage 1 <38%, 2 <76%, 3 ≥76%; auto-advance at 100% | UI | Yes | High | Test clock | Not run
TC-026 | LS-083 | FR-09 | SCR-08 | en | Cancel and retry | Generating | Tap ✕; tap Try again | Paused state; retry restarts progress | UI | Yes | High | – | Not run
TC-027 | LS-083 | FR-09 | SCR-08 | en | Back to idea keeps text | Paused | Tap Back to your idea | Create opens with previous text intact | UI | Yes | Medium | – | Not run
TC-028 | LS-084 | FR-10 | SCR-09 | kn | Generated in Kannada | Story language ಕನ್ನಡ | Generate story | Story Ready shows Kannada title, synopsis, peek | Localization | Yes | High | – | Not run
TC-029 | LS-084 | FR-10 | SCR-09 | en | Auto-saved to Created by Me | Story ready | Tap Saved row | My Stories opens on Created by Me with the story | Integration | Yes | High | – | Not run
TC-030 | LS-090 | FR-11 | SCR-10 | en | Pagination bounds | On Reader page 1 | Check Previous; go to last page; check Next | Previous disabled on 1; Next disabled on last | UI | Yes | High | 5-page story | Not run
TC-031 | LS-090 | FR-11 | SCR-10 | en | Text size limits | On Reader | Tap A+ ×5, A− ×10 | Scale clamps at 1.3 and 0.9 | Unit | Yes | Medium | – | Not run
TC-032 | LS-090 | NFR-04 | SCR-10 | kn | Kannada reading at 200% font | System font 2.0, ಕನ್ನಡ | Open Reader | Text wraps, scrolls, no clipping | Accessibility | Partly | High | – | Not run
TC-033 | LS-091 | FR-24 | SCR-03 | en | Resume reading | Read to page 3 | Relaunch; tap continue | Opens at page 3 / saved position | Integration | Yes | Medium | – | Not run
TC-034 | LS-092 | FR-12 | SCR-11a | en | Play/pause & ±15 s | On Player | Play, pause, +15, −15 | State and time update; times formatted mm:ss | Unit | Yes | High | 8:00 track | Not run
TC-035 | LS-092 | FR-12 | SCR-11a | en | Speed cycle | On Player | Tap Speed ×4 | 1× → 1.25× → 1.5× → 0.75× → 1× | Unit | Yes | Low | – | Not run
TC-036 | LS-092 | NFR-12 | SCR-11a | en | Simulation disclosed | On Player | Inspect screen | Simulated narration indicated | UI | Yes | High | – | Not run
TC-037 | LS-093 | FR-12 | SCR-11b | en | Sleep timer select | On Player | Open sheet; choose 15 minutes | Sheet closes; button reads '15 minutes' | UI | Yes | Medium | – | Not run
TC-038 | LS-100 | FR-14 | SCR-12 | en | Tabs filter | Library has created, downloaded, favourite | Switch each tab | Correct subsets | UI | Yes | High | Seed | Not run
TC-039 | LS-100 | FR-14 | SCR-12 | en | Downloaded empty state | No downloads | Open Downloaded tab | 'Ready for offline adventures?' + Discover stories | UI | Yes | Medium | – | Not run
TC-040 | LS-101 | FR-15 | SCR-17 | en | Remove download | 1 download | Tap ✕ | Row removed; storage total updates; empty state | UI | Yes | Medium | – | Not run
TC-041 | LS-110 | FR-16 | SCR-13 | en | Toggle independent of row | On Profile | Tap toggle; tap row text | Toggle flips without navigating; row navigates | UI | Yes | High | – | Not run
TC-042 | LS-063 | FR-03 | SCR-14 | en | Switch active child | 2 profiles | Tap Switch on Ananya | Ananya Active; Home shows 'Stories for Ananya' | Integration | Yes | High | Aarav, Ananya | Not run
TC-043 | LS-111 | FR-17 | SCR-16 | en | Disable reminder | On Reminder | Turn toggle off | Time and days disabled | UI | Yes | Low | – | Not run
TC-044 | LS-111 | FR-17 | SCR-16 | kn | Saved toast time format | ಕನ್ನಡ | Save reminder 20:30 | Toast shows locale-formatted time in Kannada | Localization | Yes | Low | – | Not run
TC-045 | LS-112 | FR-18 | SCR-18 | en | Mark all read | Unread exists | Tap Mark all read | Unread dots removed | UI | Yes | Low | – | Not run
TC-046 | LS-113 | FR-19 | SCR-15 | en | Demo plan confirmation | Flag on | Select Monthly; tap CTA; Done | Dialog says no payment; returns Home | UI | Yes | Low | – | Not run
TC-047 | LS-113 | NFR-07 | SCR-15 | en | No billing in build | – | Inspect merged manifest & deps | No billing permission/library | Security | Yes | High | – | Not run
TC-048 | LS-040 | FR-20 | All | en→kn | Change language mid-journey | On Reader page 2 | Change app language to ಕನ್ನಡ | Same story/page retained; UI in Kannada; no crash | Integration | Yes | Highest | – | Not run
TC-049 | LS-040 | FR-20 | All | kn | Fallback when KN missing | Test build with one KN key removed | Open affected screen | English shown, no raw key/crash (CI also fails parity) | Localization | Yes | High | – | Not run
TC-050 | LS-041 | NFR-02 | – | – | Translation parity CI | – | Remove a KN key; run check | Build fails with key name | Build/CI | Yes | High | – | Not run
TC-051 | LS-034 | NFR-01 | – | – | Hardcoded text blocked | – | Add Text("Hello") in feature | Lint/detekt fails | Build/CI | Yes | High | – | Not run
TC-052 | LS-042 | NFR-03 | Key screens | en-XA | Pseudo-locale expansion | Debug build | Run screenshots in en-XA | No clipping/overlap | Screenshot | Yes | Medium | – | Not run
TC-053 | LS-123 | NFR-04 | All | en | Touch targets | – | Accessibility Scanner on each screen | All targets ≥48dp | Accessibility | Partly | High | – | Not run
TC-054 | LS-123 | NFR-04 | All | en/kn | TalkBack labels | TalkBack on | Traverse each screen | All controls labelled in current language; logical order | Accessibility | No | High | – | Not run
TC-055 | LS-012 | NFR-04 | SCR-01, SCR-08, SCR-11a | en | Reduced motion | Remove animations ON | Open animated screens | Twinkle animations disabled | Accessibility | Yes | Medium | – | Not run
TC-056 | LS-030 | NFR-09 | – | – | Build on Windows & macOS | Clean clone | gradlew.bat assembleDebug / ./gradlew assembleDebug | Both succeed; no git diffs | Build/CI | Partly | High | – | Not run
TC-057 | LS-051 | FR-25 | SCR-19 | en | First-run routing | Fresh install vs returning | Launch twice | 1st → Onboarding; 2nd → Home | UI | Yes | High | – | Not run
TC-058 | LS-062 | NFR-11 | SCR-03 | en | Process death | Profile set | Kill process from background; reopen | State restored | Integration | Yes | Medium | – | Not run
TC-059 | LS-041 | NFR-03 | – | all | Registry matches locales_config.xml | Registry and locales_config.xml exist | Run unit test comparing SupportedLanguage entries with locales_config.xml | Same locale set; test fails on mismatch | Localization | Yes | High | Registry + XML | Not run
TC-060 | LS-036 | FR-21 | SCR-04a, SCR-06 | en, kn | Mock content parity per story ID | stories_en.json and stories_kn.json present | Run parity check over all story IDs | Every ID exists in both files or is listed as expected English fallback (story_lanterns_jaipur) | Localization | Yes | High | docs/testing/test-data.md seed set | Not run
TC-061 | LS-080 | FR-08 | SCR-07 | kn | Kannada keyboard input in Create | App in Kannada, Kannada IME installed | Type a Kannada sentence in What happened today; submit | Text accepted, counter counts characters correctly, no clipping | UI | Partly | Medium | Kannada sample sentence | Not run

## Dependencies
Ticket | Summary | Dependencies | Critical Predecessor | Blocks | Parallelizable | Shared Files | Shared Module / API Contract | Conflict Risk | Integration Checkpoint | Branch / Worktree Strategy | Conditions for Starting | Conditions for Completion
LS-001 | Read-only repository & toolchain discovery | None | – | LS-003, LS-005, LS-007, LS-008, LS-030, LS-131 | Yes | – | Repo / tooling | Low | P0 exit: Report delivered | Own branch/worktree off development; rebase after dependency merges | Approval A | DoD met; PR merged by owner; post-merge verification passed
LS-002 | Extract Figma Make design: screen inventory, tokens, specs | None | – | LS-003, LS-004, LS-008 | Yes | – | Design | Low | P0 exit: Report delivered | Own branch/worktree off development; rebase after dependency merges | Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-003 | Requirements catalogue, user journeys A–G and edge cases | LS-001, LS-002 | LS-002 | LS-006 | Yes | – | Docs | Low | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-004 | Resolve design gaps & open product decisions | LS-002 | LS-002 | LS-046, LS-051, LS-111, LS-113, LS-114, LS-115 | Yes | – | Docs / Design | Low | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-005 | CLAUDE.md and .github/copilot-instructions.md | LS-001 | LS-001 | – | Yes | CLAUDE.md, .github/copilot-instructions.md | Repo root | Medium | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-006 | Prompt library (prompts/00–21) and per-ticket prompts | LS-003, LS-008 | LS-008 | – | Yes | – | prompts/ | Low | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-007 | Commit backlog workbook and design reference pack to docs/ | LS-001 | LS-001 | – | Yes | – | Docs | Low | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-008 | Architecture ADRs (ADR-001…015) | LS-001, LS-002 | LS-002 | LS-006, LS-030, LS-031 | Yes | – | Docs / Architecture | Low | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-010 | Colour tokens → Compose theme | LS-031 | LS-031 | LS-014, LS-015, LS-018, LS-150 | After deps | core/designsystem/theme/Color.kt | :core:designsystem | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-011 | Typography: DM Sans + Manrope + Kannada fallback, type scale | LS-031 | LS-031 | LS-014, LS-015 | After deps | core/designsystem/theme/Type.kt, res/font | :core:designsystem | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-012 | Shape, spacing, elevation and motion tokens | LS-031 | LS-031 | LS-015, LS-018 | After deps | core/designsystem/theme/Dimens.kt, Shape.kt, Motion.kt | :core:designsystem | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-013 | Icon set (21 line icons) as vector drawables | LS-031 | LS-031 | LS-019, LS-094 | Yes | – | :core:designsystem | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-014 | LittleStory brand mark composable (default + light) | LS-010, LS-011 | LS-011 | LS-060 | Yes | – | :core:designsystem | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-015 | Buttons and IconButton components | LS-010, LS-011, LS-012 | LS-012 | LS-016, LS-017, LS-018, LS-019, LS-020 | After deps | – | :core:designsystem | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-016 | Form components: text field, select, chips, segmented, toggle, search, tabs | LS-015 | LS-015 | LS-020, LS-061, LS-071, LS-080, LS-100, LS-110 | After deps | – | :core:designsystem | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-017 | Feedback components: bottom sheet, dialog, toast, empty state, notes banner, progress bars | LS-015 | LS-015 | LS-020, LS-060, LS-072, LS-083, LS-092, LS-101, LS-113 | After deps | – | :core:designsystem | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-018 | Story components: StoryArt, StoryCard, ListStoryRow, ContinueCard, SectionHeader, Avatar | LS-010, LS-012, LS-015 | LS-015 | LS-020, LS-070, LS-071, LS-073, LS-074, LS-084, LS-090, LS-092, LS-100, LS-101 | After deps | – | :core:ui | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-019 | Navigation chrome: TopBar, BottomNav, sticky action bars | LS-013, LS-015 | LS-015 | LS-020, LS-050 | After deps | – | :core:ui | Medium | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-020 | Design-system catalogue & screenshot baselines (EN/KN) | LS-015, LS-016, LS-017, LS-018, LS-019, LS-035 | LS-035 | – | After deps | – | :core:designsystem | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-030 | Project baseline: Gradle wrapper, version catalog, JDK toolchain, .gitattributes | LS-001, LS-008, LS-009, LS-039 | LS-008 | LS-031, LS-130, LS-132 | No | settings.gradle.kts, gradle/libs.versions.toml, .gitattributes | Build | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-031 | Module structure + build-logic convention plugins | LS-030, LS-008 | LS-008 | LS-010, LS-011, LS-012, LS-013, LS-032, LS-033, LS-034, LS-035, LS-037, LS-040, LS-050 | No | settings.gradle.kts, build-logic/ | Build | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-032 | Dependency injection (Hilt) and Application entry | LS-031 | LS-031 | – | After deps | app/build.gradle.kts, AndroidManifest.xml | :app | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-033 | Central configuration & feature flags (AppConfig) | LS-031 | LS-031 | LS-080, LS-082, LS-092, LS-113, LS-150 | After deps | core/common/config/AppConfig.kt | :core:common | Medium | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-034 | Lint & static analysis rules (hardcoding, translations) | LS-031 | LS-031 | LS-125, LS-130 | After deps | lint.xml, detekt.yml | Build | Medium | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-035 | Test infrastructure (unit, UI, screenshot) | LS-031 | LS-031 | LS-020, LS-122 | After deps | gradle/libs.versions.toml | Build / test | Medium | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-036 | Mock data sources: per-language JSON assets + loader | LS-037 | LS-037 | LS-044, LS-070, LS-071, LS-073, LS-074, LS-082, LS-090, LS-112 | After deps | – | :data | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-037 | Domain models & repository interfaces | LS-031 | LS-031 | LS-036, LS-038, LS-082, LS-140 | After deps | domain/model/*, domain/repository/* | :domain | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-038 | Local persistence (DataStore + Room per ADR-004) | LS-037 | LS-037 | LS-051, LS-062, LS-075, LS-091, LS-101, LS-111 | After deps | – | :data | Medium | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-040 | Localization foundation: EN/KN resources, locale switching, language registry, UiText | LS-031 | LS-031 | LS-041, LS-042, LS-043, LS-045, LS-046, LS-048, LS-081, LS-150 | After deps | locales_config.xml, SupportedLanguage.kt | :core:common / :core:ui | High | P2 exit: Build + tests + lint green | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-041 | Translation completeness check (key & format-arg parity) in Gradle/CI | LS-040 | LS-040 | LS-048, LS-130 | After deps | – | Build | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-042 | Pseudo-locales & RTL readiness | LS-040 | LS-040 | – | Yes | – | :app | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-043 | Kannada UI strings (draft) + glossary | LS-040 | LS-040 | LS-047 | Yes | – | Resources | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-044 | Kannada mock story content | LS-036 | LS-036 | LS-047 | Yes | – | :data assets | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-045 | Language selection in Setup (registry-driven) | LS-040, LS-061 | LS-061 | – | After deps | – | :feature:onboarding | Low | P3 exit: Journey A verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-046 | Language preferences screen (from Profile) | LS-004, LS-040, LS-110 | LS-110 | – | After deps | – | :feature:settings | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-047 | Native Kannada review & sign-off | LS-043, LS-044, LS-122 | LS-122 | LS-133 | After deps | – | Resources | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-048 | 'How to add a new language' guide + prompt | LS-040, LS-041 | LS-041 | – | Yes | – | Docs | Low | P8 exit: Owner sign-off | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-050 | Navigation graph with typed routes for all screens | LS-019, LS-031 | LS-031 | LS-051, LS-052, LS-060, LS-061, LS-070, LS-071, LS-073, LS-074, LS-080, LS-090, LS-110, LS-112 | No | AppNavHost.kt, Destinations.kt | :app / navigation | High | P3 exit: Journey A verified | Single owner; run sequentially; own worktree off latest development | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-051 | Splash screen & first-run routing | LS-004, LS-050, LS-038 | LS-038 | – | After deps | – | :app | Low | P3 exit: Journey A verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-052 | Edge-to-edge & system bar styling | LS-050 | LS-050 | – | After deps | – | :core:ui | Low | P3 exit: Journey A verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-060 | Onboarding – 3 slides | LS-050, LS-017, LS-014 | LS-014 | LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:onboarding | Low | P3 exit: Journey A verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-061 | Setup – child profile form | LS-016, LS-062, LS-050 | LS-050 | LS-045, LS-063, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:onboarding | Low | P3 exit: Journey A verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-062 | Profile repository & active-child state | LS-038 | LS-038 | LS-061, LS-063, LS-070, LS-080, LS-110, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :data | Low | P3 exit: Journey A verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-063 | Child Profiles – list, switch, edit, add | LS-062, LS-061 | LS-061 | LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:profiles | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-070 | Home screen | LS-018, LS-050, LS-062, LS-036 | LS-036 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:home | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-071 | Discover – search, featured, filters, grid, rows | LS-018, LS-016, LS-036, LS-050 | LS-050 | LS-072, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:discover | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-072 | Discover – no-results empty state | LS-071, LS-017 | LS-017 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:discover | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-073 | Category screen (generic, sortable) | LS-018, LS-036, LS-050 | LS-050 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:discover | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-074 | Story Detail screen | LS-018, LS-036, LS-050, LS-075 | LS-075 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:storydetails | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-075 | Favourites (shared, persisted) | LS-038 | LS-038 | LS-074, LS-100, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :data / :domain | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-080 | Create a Story – form | LS-016, LS-062, LS-033, LS-050 | LS-050 | LS-081, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:create | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-081 | Create – more options & validation | LS-080, LS-040 | LS-040 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:create | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-082 | Simulated generation repository & use case | LS-037, LS-036, LS-033 | LS-033 | LS-083, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126, LS-141 | Yes | – | :data / :domain | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-083 | Generating screen + paused state | LS-082, LS-017 | LS-017 | LS-084, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:create | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-084 | Story Ready screen | LS-083, LS-018 | LS-018 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:create | Low | P4 exit: Journeys B, C verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-090 | Reader screen | LS-018, LS-036, LS-050 | LS-050 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:reader | Low | P5 exit: Journeys D, F verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-091 | Reading & listening progress persistence | LS-038 | LS-038 | LS-092, LS-100, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :data | Low | P5 exit: Journeys D, F verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-092 | Simulated audio player | LS-018, LS-017, LS-091, LS-033 | LS-033 | LS-093, LS-094, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:player | Low | P5 exit: Journeys D, F verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-093 | Sleep timer bottom sheet | LS-092 | LS-092 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:player | Low | P5 exit: Journeys D, F verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-094 | Fix overlapping 15 s rewind/forward glyphs | LS-092, LS-013 | LS-013 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:player | Low | P5 exit: Journeys D, F verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-100 | My Stories library | LS-018, LS-016, LS-075, LS-091 | LS-091 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:library | Low | P5 exit: Journeys D, F verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-101 | Simulated downloads + Offline Downloads screen | LS-038, LS-018, LS-017 | LS-017 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:library | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-110 | Profile / settings hub | LS-016, LS-050, LS-062 | LS-062 | LS-046, LS-111, LS-114, LS-115, LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | After deps | – | :feature:settings | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-111 | Bedtime Reminder settings | LS-110, LS-038, LS-004 | LS-004 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:settings | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-112 | Notifications inbox (mock) | LS-050, LS-036 | LS-036 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:notifications | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-113 | Demo subscription (feature-flagged) + dialog | LS-017, LS-033, LS-004 | LS-004 | LS-120, LS-121, LS-122, LS-123, LS-125, LS-126 | Yes | – | :feature:subscription | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-114 | Privacy & parent controls screen | LS-004, LS-110 | LS-110 | LS-126 | After deps | – | :feature:settings | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-115 | Help & about screen | LS-004, LS-110 | LS-110 | LS-126 | After deps | – | :feature:settings | Low | P6 exit: Journeys E, G verified | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-120 | Unit-test coverage gate for ViewModels & use cases | LS-070…LS-113 | LS-113 | – | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-121 | End-to-end journey tests A–G (EN & KN) | LS-060…LS-113 | LS-113 | LS-133 | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-122 | Screenshot regression suite – 22 design states × EN/KN | LS-035, LS-060…LS-113 | LS-035 | LS-047, LS-124, LS-133 | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-123 | Accessibility audit & fixes | LS-060…LS-113 | LS-113 | LS-133 | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-124 | Visual fidelity review vs design pack | LS-122 | LS-122 | – | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-125 | Maintainability review – hardcoded values audit | LS-034, LS-060…LS-113 | LS-034 | – | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-126 | Security & privacy review + threat model | LS-060…LS-115 | LS-115 | LS-133 | After deps | – | All | Low | P7 exit: All Must tests pass | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-130 | GitHub Actions PR workflow | LS-030, LS-034, LS-041 | LS-041 | – | After deps | .github/workflows/ci.yml | .github/workflows | Medium | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval C | DoD met; PR merged by owner; post-merge verification passed
LS-131 | Branch strategy, PR template, CODEOWNERS | LS-001 | LS-001 | – | Yes | – | .github | Low | P1 exit: Docs approved | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-132 | Build & run docs (Windows + macOS), release checklist, known limitations | LS-030 | LS-030 | – | Yes | – | Docs | Low | P8 exit: Owner sign-off | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-133 | Release-readiness report | LS-121, LS-122, LS-123, LS-126, LS-047 | LS-047 | – | After deps | – | Docs | Low | P8 exit: Owner sign-off | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-140 | Proposed future API contracts (incl. language negotiation) | LS-037 | LS-037 | – | Yes | – | Docs | Low | P8 exit: Owner sign-off | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-141 | AI generation flow & multilingual child-safety plan | LS-082 | LS-082 | – | Yes | – | Docs | Low | P8 exit: Owner sign-off | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
LS-150 | Configuration docs & 'How to change X' guide | LS-033, LS-010, LS-040 | LS-040 | – | Yes | – | Docs | Low | P2 exit: Build + tests + lint green | Own branch/worktree off development; rebase after dependency merges | Deps merged to development; Approval B | DoD met; PR merged by owner; post-merge verification passed
Parallel lanes (after P2 foundation)
Sequential foundation (single owner) |  | LS-030 → LS-031 → LS-037 / LS-040 / LS-010–012 → LS-050 (root Gradle, catalog, tokens, registry, nav graph)
Lane A – Onboarding & profiles |  | LS-060, LS-061, LS-062, LS-045, LS-063
Lane B – Discovery |  | LS-070, LS-071, LS-072, LS-073, LS-074, LS-075
Lane C – Creation |  | LS-080, LS-081, LS-082, LS-083, LS-084
Lane D – Reader, player, library |  | LS-090, LS-091, LS-092, LS-093, LS-094, LS-100, LS-101
Lane E – Settings & parent |  | LS-110, LS-111, LS-112, LS-113, LS-046, LS-114, LS-115
Anytime (docs / content) |  | LS-003–LS-008, LS-043, LS-044, LS-131, LS-140, LS-141, LS-150
LS-009 | Repository hygiene: default branch main, development branch | LS-001 | LS-001 | LS-030, LS-131 | Yes | GitHub settings | – | Low | P1 exit | Owner action, no branch | Owner decision D2 | Default branch main; development exists
LS-039 | Build verification environment (ADR-017) | LS-009 | LS-009 | LS-030, LS-035, LS-130 | Yes | Cloud environment settings | – | Low | P2 entry | Owner action, no branch | Owner decision D3 | Gradle sync downloading AGP succeeds

## ADRs
ADR ID | Decision Title | Context | Options Considered | Decision | Rationale | Consequences | Status | Approver | Date | Related Tickets
ADR-001 | Navigation library | Need typed navigation for ~22 destinations | Navigation-Compose 2 (type-safe routes) · Navigation 3 | Recommended: Navigation Compose type-safe routes; re-check Navigation 3 in LS-030 | Pick most stable with verified AGP/Kotlin compatibility | Affects all feature modules | Proposed | Project owner |  | LS-050
ADR-002 | Module structure | Small MVP, many features, parallel agents | Single module · layered · feature modules | Recommended (D4): 7 feature modules — onboarding, home, discover, create, reader, library, settings — plus app, build-logic, core:designsystem, core:ui, core:common, domain, data | Parallel work with low conflicts | More Gradle setup → convention plugins | Proposed | Project owner |  | LS-031
ADR-003 | Dependency injection | Repositories swapped mock → real later | Hilt · Koin · manual | Hilt | Standard, testable, compile-time | Annotation processing (KSP) | Proposed | Project owner |  | LS-032
ADR-004 | Persistence | Favourites, profiles, progress, downloads, settings must survive restart | DataStore only · Room + DataStore | Room for relational data; DataStore for preferences | Queries for library tabs; simple prefs | Migration discipline | Proposed | Project owner |  | LS-038
ADR-005 | Locale switching | EN/KN now, more later; Android 13 per-app language | AppCompat per-app locales · custom context wrapper | AppCompatDelegate.setApplicationLocales + locales_config.xml | Official, persists automatically, system settings integration | Verify minSdk behaviour | Proposed | Project owner |  | LS-040
ADR-006 | Supported language registry | Avoid scattered language lists (design lists 7) | Enum · config file · resources | SupportedLanguage registry (tag, native name, enabled, default) | Single source; tests can check locales_config parity | – | Proposed | Project owner |  | LS-040, LS-045, LS-046
ADR-007 | Localized mock content | Stories must exist in EN & KN | String resources · per-language JSON assets | assets/mock/*_{tag}.json keyed by stable IDs; EN fallback | Scales to more stories/languages; mirrors future API | Loader + parity check needed | Proposed | Project owner |  | LS-036, LS-044
ADR-008 | Fonts | DM Sans/Manrope have no Kannada glyphs | Downloadable fonts · bundled fonts | Bundle DM Sans + Manrope + Noto Sans Kannada (all OFL) in res/font | Offline, deterministic screenshots | APK size (+~1 MB) | Proposed | Project owner |  | LS-011
ADR-009 | UiText abstraction | ViewModels must not hold translated strings | Resource IDs · UiText sealed type | UiText (StringRes, PluralRes, Dynamic) | Testable, language-agnostic VMs | Small boilerplate | Proposed | Project owner |  | LS-040
ADR-010 | Story artwork | Design art is CSS-drawn, no image assets | Compose Canvas · vector drawables · commissioned PNGs | Compose Canvas driven by story palette + motif | Matches design, themable, tiny size | Drawing effort (LS-018) | Proposed | Project owner |  | LS-018
ADR-011 | Screenshot testing | Need EN/KN visual regression | Compose Preview Screenshot Testing · Roborazzi · Paparazzi | Recommended (D7): Roborazzi; Compose Preview Screenshot Testing as alternative | Compatibility with AGP version | CI runtime | Proposed | Project owner |  | LS-035, LS-122
ADR-012 | Configuration & feature flags | No hardcoding; simulated features | Scattered constants · AppConfig objects + BuildConfig | AppConfig (limits, timings, options) + FeatureFlags + BuildConfig | One place to change | – | Proposed | Project owner |  | LS-033
ADR-013 | Theme | Design has cream light UI + night screens; no dark mode | Light only · light + dark | Single light theme with 'night' surface tokens; dark mode out of MVP | Matches design | System dark mode ignored – document | Proposed | Project owner |  | LS-010
ADR-014 | Simulated features policy | No real AI/audio/billing/notifications in MVP | – | Simulations behind interfaces + visible labelling + flags | Honest UX, swappable later | – | Proposed | Project owner |  | LS-082, LS-092, LS-101, LS-113
ADR-015 | Bedtime reminder delivery | Design shows reminder setting; remote notifications excluded | Settings only · local scheduled notification | Recommended (D13): settings UI only in MVP; real local notification is a separate approved ticket | Local notification needs POST_NOTIFICATIONS & alarm scheduling | Permission + testing | Pending Approval | Project owner |  | LS-111
ADR-016 | Minimum SDK | Compatibility for Kannada rendering and per-app language | minSdk 24 · 26 · 28 | Recommended (D5): minSdk 26 | Predictable font + per-app-language behaviour; AppCompat backport below Android 13 | Android 7.x unsupported | Proposed | Project owner | 29 Oct 2026 | LS-030, LS-040
ADR-017 | Build and test verification environment | Cloud agent workspace cannot reach dl.google.com (R-21) | Allow host · CI only · owner machine only | Recommended (D3): allow dl.google.com + GitHub Actions on every PR | PRs need real build evidence | CI becomes part of the foundation milestone | Proposed | Project owner | 29 Oct 2026 | LS-039, LS-130
ADR-018 | Static analysis | No-hardcoding policy needs enforcement | Lint only · Lint + Detekt · Lint + Detekt + ktlint | Recommended (D15): Lint (errors) + Detekt + ktlint | Catches magic numbers, raw colours/dp and style drift | Rules maintained in build-logic | Proposed | Project owner | 29 Oct 2026 | LS-034

## Risks & Questions
ID | Risk / Question | Category | Description | Probability | Impact | Mitigation | Owner | Required Decision | Deadline / Milestone | Status
R-01 | Old brand in design assets | Design | Screenshots show 'LittleKatha' in logo, Profile group header and Premium banner | High | Low | Rebuild brand mark with 'LittleStory'; grep check in CI | Owner | Confirm final logo | P2 | Open
R-02 | Design offers 7 languages | Scope | Setup/Create language lists show English, Hindi, Kannada, Tamil, Telugu, Marathi, Malayalam | High | Medium | Registry-driven list exposing only EN/KN | Owner | Confirm EN/KN only for MVP | P1 | Open
R-03 | Fonts lack Kannada glyphs | Localization | DM Sans and Manrope do not cover Kannada script | High | High | Noto Sans Kannada fallback + KN line-height tokens | Localization Eng. | Approve fallback font | P2 | Open
R-04 | Kannada text expansion | Localization | 10sp nav labels, chips, buttons, tabs may clip | High | Medium | Flexible layouts, pseudo-locale tests, KN screenshots | Localization Eng. | Accept wrapping rules | P3–P6 | Open
R-05 | Missing designs | Design | Splash, Language preferences, Privacy & parent controls, Help & about, Account settings, Audio preferences, notifications empty state | High | Medium | Simple pattern-based screens approved by owner | Owner | Provide designs or approve patterns | P1 | Open
R-06 | Gendered sample copy | Content | Placeholder 'helped his friend' assumes gender; hard to translate | Medium | Low | Neutral copy using child name | Owner | Approve copy | P1 | Open
R-07 | Low contrast secondary text | Accessibility | Measured 29 Oct 2026 (docs/design/accessibility-spec.md): muted #716B80 passes (4.87:1 on cream, 5.10:1 on white); nav-inactive #817B8D fails (3.89:1 on cream), lavender focus ring on white 2.53:1 and progress fill on track 2.02:1 fail non-text 3:1 | High | Medium | Darken nav-inactive token; thicker/darker focus ring and progress fill | Accessibility Eng. | Approve token change | P7 | Open
R-08 | Small touch targets | Accessibility | Chips and 42px icon buttons below 48dp | High | Medium | Expand touch area without changing visuals | Accessibility Eng. | – | P2 | Open
R-09 | No motion spec for transitions | Design | Screens swap instantly; sheets don't slide; toasts don't auto-dismiss | Medium | Low | Use platform defaults; record decision | Owner | Choose transitions | P1 | Open
R-10 | Greeting fixed to 'Good evening' | Content | No time-of-day variants designed | Medium | Low | Morning/afternoon/evening strings or keep fixed | Owner | Decide | P1 | Open
R-11 | Child & parent personal data | Privacy | Parent name, email (example) and child details collected | Medium | High | Collect minimum; local only; no email in MVP; delete action | Security Reviewer | Confirm fields | P1 | Open
R-12 | Native Kannada reviewer | Localization | Translations need fluent reviewer before release | Medium | High | Name reviewer early; review in batches | Owner | Assign reviewer | P6 | Open
R-13 | Kannada TTS for TalkBack | Accessibility | Device may lack Kannada voice | Medium | Medium | Document limitation; test on device with voice | Accessibility Eng. | – | P7 | Open
R-14 | Reminder scheduling | Scope | Real reminders need POST_NOTIFICATIONS + scheduling | Medium | Medium | Settings-only in MVP unless approved (ADR-015) | Owner | Decide | P1 | Open
R-15 | Demo pricing perceived as real | Compliance | ₹ prices shown | Low | Medium | Feature flag + explicit disclaimer; no billing code | Owner | Ship or hide | P6 | Open
R-16 | Illustration fidelity effort | Delivery | CSS-drawn art must be recreated in Compose | Medium | Medium | ADR-010; prioritise 6 motifs | UI Eng. | – | P2 | Open
R-17 | Repository state unknown | Delivery | Discovery (LS-001) not yet run | High | High | Closed by P0 assessment 29 Oct 2026: repo is docs-only (see R-21, R-22) | Orchestrator | – | P0 | Closed
R-18 | Category screen hard-coded | Design | Prototype only shows Indian Tales; hero art per category undefined | Medium | Low | Generic screen + per-category data | Owner | Approve generic hero | P4 | Open
R-19 | Prototype placeholder routes | Design | Several settings rows route to unrelated screens | High | Medium | Map to real or disabled destinations (LS-004) | Owner | Decide per row | P1 | Open
R-20 | 15 s control glyph overlap | Design defect | '15' and arrow glyphs overlap on Player | High | Low | LS-094 – proper icons | UI Eng. | – | P5 | Open
R-21 | Build environment blocked | Delivery | Cloud agent workspace gets 403 for dl.google.com (Google Maven, Android SDK); agents cannot build Android there | High | High | Allow dl.google.com in cloud environment; GitHub Actions CI; no unverified build claims (ADR-017, LS-039) | Owner | Choose build environment (D3) | P2 | Open
R-22 | Default branch misconfigured | Delivery | GitHub default branch is the docs branch claude/project-thread-sszyf7, not main | High | Medium | Owner merges PR #1, sets default to main, creates development (LS-009) | Owner | Approve repo hygiene (D2) | P1 | Open
R-23 | Design drift | Design | Agents cannot re-read the Figma Make file; docs/design/ is a 29 Oct 2026 snapshot | Medium | Medium | Owner flags Make changes; re-export the design pack | Owner | – | P1–P7 | Open
R-24 | Public repository | Security | Repository is public; secrets or child data committed would be exposed | Medium | High | Secret scanning in CI; .gitignore local.properties/keystores; synthetic data only | Security Reviewer | Keep public or make private | P1 | Open

## Git-PR-CI
Ticket | Branch | Base Branch | PR URL | Build | Unit Tests | UI Tests | Screenshot Diff (EN/KN) | Lint (Hardcoded/MissingTranslation) | Translation Completeness | Security Check | Reviewer Status | Merge Status | Human Approval | Post-Merge Verification | Release Status
LS-001 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-002 | – (no code) | – | – | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LS-003 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-004 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-005 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-006 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-007 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-008 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-010 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-011 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-012 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-013 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-014 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-015 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-016 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-017 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-018 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-019 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-020 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-030 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-031 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-032 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-033 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-034 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-035 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-036 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-037 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-038 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-040 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-041 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-042 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-043 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-044 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-045 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-046 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-047 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-048 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-050 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-051 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-052 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-060 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-061 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-062 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-063 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-070 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-071 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-072 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-073 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-074 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-075 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-080 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-081 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-082 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-083 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-084 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-090 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-091 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-092 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-093 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-094 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-100 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-101 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-110 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-111 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-112 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-113 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-114 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-115 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-120 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-121 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-122 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-123 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-124 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-125 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-126 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-130 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-131 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-132 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-133 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-140 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-141 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-150 |  | development |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
LS-009 | – | – | – | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LS-039 | – | – | – | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Translations
String Key | Module / File | English (values/) | Kannada (values-kn/) | Context / Screen | Max Length / Constraint | Translation Status | Reviewer | Notes
app_name | app · strings.xml | LittleStory |  | Brand wordmark | Do not translate (brand) – confirm | Missing
app_tagline | core:ui · strings.xml | Little Stories. Big Imagination. |  | Onboarding eyebrow (uppercased by style) | Single line | Missing
action_continue | core:ui · strings.xml | Continue |  | Buttons | Button | Missing
action_skip | core:ui · strings.xml | Skip |  | Onboarding | Short | Missing
action_back | core:ui · strings.xml | Go back |  | Back button content description | A11y | Missing
action_see_all | core:ui · strings.xml | See all |  | Section headers | Short link | Missing
action_view_all | core:ui · strings.xml | View all |  | Discover | Short link | Missing
action_cancel | core:ui · strings.xml | Cancel |  | Sheets | Button | Missing
action_done | core:ui · strings.xml | Done |  | Dialog | Button | Missing
action_try_again | core:ui · strings.xml | Try again |  | Generating paused | Button | Missing
action_download | core:ui · strings.xml | Download |  | Detail, Player | Short | Missing
state_downloaded | core:ui · strings.xml | Downloaded |  | Player | Short | Missing
action_favourite | core:ui · strings.xml | Favourite |  | Player | Short | Missing
state_loved | core:ui · strings.xml | Loved |  | Player | Short | Missing
cd_favourite_add | core:ui · strings.xml | Add to favourites |  | Heart button | A11y | Missing
cd_favourite_remove | core:ui · strings.xml | Remove from favourites |  | Heart button | A11y | Missing
cd_open_story | core:ui · strings.xml | Open %1$s |  | Story card | A11y; %1$s = title | Missing
cd_notifications | core:ui · strings.xml | Notifications |  | Bell | A11y | Missing
cd_profile_of | core:ui · strings.xml | %1$s’s profile |  | Avatar | A11y | Missing
label_available_offline | core:ui · strings.xml | Available offline |  | Rows | Short | Missing
label_available | core:ui · strings.xml | Available |  | Narration row | Short | Missing
meta_minutes | core:ui · strings.xml | %1$d min |  | Story meta | Plural | Missing
meta_category_minutes | core:ui · strings.xml | %1$s · %2$d min |  | Story card | Format | Missing
meta_ages | core:ui · strings.xml | Ages %1$s |  | Detail, Category | Format | Missing
nav_home | core:ui · strings.xml | Home |  | Bottom nav | ≤1 line at 10sp | Missing
nav_discover | core:ui · strings.xml | Discover |  | Bottom nav | ≤1 line at 10sp | Missing
nav_create | core:ui · strings.xml | Create |  | Bottom nav | ≤1 line at 10sp | Missing
nav_my_stories | core:ui · strings.xml | My Stories |  | Bottom nav | ≤1 line at 10sp | Missing
nav_profile | core:ui · strings.xml | Profile |  | Bottom nav | ≤1 line at 10sp | Missing
onboarding_1_title | feature:onboarding · strings.xml | Every Day Has a Story |  | SCR-01 slide 1 | Title ≤2 lines | Missing
onboarding_1_body | feature:onboarding · strings.xml | Turn school days, family moments and tiny acts of kindness into magical adventures. |  | SCR-01 | Body | Missing
onboarding_2_title | feature:onboarding · strings.xml | Your Child, the Hero |  | SCR-01 slide 2 | Title ≤2 lines | Missing
onboarding_2_body | feature:onboarding · strings.xml | Stories shaped around their name, age and favourite things—with parents always in control. |  | SCR-01 | Body | Missing
onboarding_3_title | feature:onboarding · strings.xml | Listen, Dream, Repeat |  | SCR-01 slide 3 | Title ≤2 lines | Missing
onboarding_3_body | feature:onboarding · strings.xml | Gentle narration, offline stories and a sleep timer make bedtime feel wonderfully calm. |  | SCR-01 | Body | Missing
onboarding_get_started | feature:onboarding · strings.xml | Get Started |  | SCR-01 | Button | Missing
onboarding_pager_cd | feature:onboarding · strings.xml | Slide %1$d of %2$d |  | Pager | A11y | Missing
setup_skip_for_now | feature:onboarding · strings.xml | Skip for now |  | SCR-02 top bar | Short | Missing
setup_trust_badge | feature:onboarding · strings.xml | Private & parent-managed |  | SCR-02 badge | Single line | Missing
setup_title | feature:onboarding · strings.xml | Let’s make stories feel like home. |  | SCR-02 | Title | Missing
setup_subtitle | feature:onboarding · strings.xml | A few details help us choose safe, age-appropriate adventures. |  | SCR-02 | Body | Missing
setup_parent_name | feature:onboarding · strings.xml | Parent name |  | Field label | Label | Missing
setup_child_name | feature:onboarding · strings.xml | Child’s name |  | Field label | Label | Missing
setup_choose_avatar | feature:onboarding · strings.xml | Choose an avatar |  | Field label | Label | Missing
setup_age | feature:onboarding · strings.xml | Age |  | Field label | Label | Missing
setup_language | feature:onboarding · strings.xml | Language |  | Field label | Label | Missing
setup_interests | feature:onboarding · strings.xml | Favourite interests |  | Field label | Label | Missing
label_optional | core:ui · strings.xml | Optional |  | Field hint | Short | Missing
setup_story_duration | feature:onboarding · strings.xml | Story duration |  | Field label | Label | Missing
duration_minutes_option | core:ui · strings.xml | %1$d min |  | Segmented/chips | Plural | Missing
setup_create_profile | feature:onboarding · strings.xml | Create %1$s’s profile |  | Sticky CTA | Button; %1$s = child name | Missing
interest_animals | core:ui · strings.xml | Animals |  | Interest/category chip | Chip | Missing
interest_cricket | core:ui · strings.xml | Cricket |  | Interest chip | Chip | Missing
interest_adventure | core:ui · strings.xml | Adventure |  | Interest/category chip | Chip | Missing
interest_space | core:ui · strings.xml | Space |  | Interest/category chip | Chip | Missing
interest_nature | core:ui · strings.xml | Nature |  | Interest/category chip | Chip | Missing
interest_music | core:ui · strings.xml | Music |  | Interest chip | Chip | Missing
home_greeting_evening | feature:home · strings.xml | Good evening |  | SCR-03 header | Short (time-of-day variants TBD) | Missing
home_title | feature:home · strings.xml | Stories for %1$s |  | SCR-03 header | %1$s = child name | Missing
home_hero_kicker | feature:home · strings.xml | Tonight’s adventure |  | Hero (uppercased by style) | Single line | Missing
home_hero_title | feature:home · strings.xml | Tonight, anything is possible. |  | Hero | ≤3 lines | Missing
home_hero_body | feature:home · strings.xml | Turn today’s little moments into magical adventures. |  | Hero | Body | Missing
home_create_story | feature:home · strings.xml | Create a Story |  | Hero button | Button | Missing
home_continue_listening | feature:home · strings.xml | Continue listening |  | Section | Heading | Missing
home_progress_label | feature:home · strings.xml | %1$d min · %2$d%% complete |  | Continue card (uppercased) | Format | Missing
home_resume_story | feature:home · strings.xml | Resume story |  | Continue card | Short | Missing
home_explore_stories | feature:home · strings.xml | Explore stories |  | Section | Heading | Missing
home_made_for | feature:home · strings.xml | Made for %1$s |  | Section | %1$s = child name | Missing
home_culture_eyebrow | feature:home · strings.xml | Rooted in wonder |  | Banner (uppercased) | Single line | Missing
home_culture_title | feature:home · strings.xml | Stories from every corner of India |  | Banner | ≤2 lines | Missing
home_culture_body | feature:home · strings.xml | Timeless wisdom, family traditions and joyful festivals. |  | Banner | Body | Missing
home_culture_link | feature:home · strings.xml | Explore Indian stories |  | Banner link | Short | Missing
category_all | core:ui · strings.xml | All |  | Filter chip | Chip | Missing
category_bedtime | core:ui · strings.xml | Bedtime |  | Category | Chip/tile | Missing
category_friendship | core:ui · strings.xml | Friendship |  | Category | Chip/tile | Missing
category_indian_tales | core:ui · strings.xml | Indian Tales |  | Category | Chip/tile | Missing
category_kindness | core:ui · strings.xml | Kindness |  | Category | Chip | Missing
category_science | core:ui · strings.xml | Science |  | Category | Chip | Missing
category_panchatantra | core:ui · strings.xml | Panchatantra |  | Category | Chip | Missing
category_indian_folk_tales | core:ui · strings.xml | Indian Folk Tales |  | Category | Chip | Missing
category_festivals | core:ui · strings.xml | Festivals |  | Category | Chip | Missing
category_learning | core:ui · strings.xml | Learning |  | Category | Chip | Missing
theme_fantasy | core:ui · strings.xml | Fantasy |  | Create theme | Chip | Missing
theme_indian_folklore | core:ui · strings.xml | Indian folklore |  | Create theme | Chip | Missing
discover_title | feature:discover · strings.xml | Discover |  | Top bar | Title | Missing
discover_search_hint | feature:discover · strings.xml | Search stories, themes, or characters |  | Search placeholder | Single line | Missing
discover_clear_search | feature:discover · strings.xml | Clear search |  | Search ✕ / empty CTA | Button/A11y | Missing
discover_featured_eyebrow | feature:discover · strings.xml | Featured this week |  | Featured card (uppercased) | Single line | Missing
discover_listen_now | feature:discover · strings.xml | Listen now |  | Featured card | Short | Missing
discover_popular | feature:discover · strings.xml | Popular right now |  | Section | Heading | Missing
discover_bedtime_favourites | feature:discover · strings.xml | Bedtime favourites |  | Section | Heading | Missing
discover_results_for | feature:discover · strings.xml | Results for “%1$s” |  | Section while searching | Format | Missing
discover_empty_title | feature:discover · strings.xml | No stories found |  | Empty state | Heading | Missing
discover_empty_body | feature:discover · strings.xml | Try a different title or explore one of our story collections. |  | Empty state | Body | Missing
category_story_count | feature:discover · strings.xml | %1$d stories |  | Category hero (uppercased) | Plural | Missing
category_indian_tales_desc | feature:discover · strings.xml | Warm, wonder-filled adventures inspired by India’s many landscapes and storytelling traditions. |  | Category hero | Body (may move to mock data) | Missing
category_list_heading | feature:discover · strings.xml | Stories for curious minds |  | SCR-05 | Heading | Missing
sort_recommended | feature:discover · strings.xml | Recommended |  | Sort | Option | Missing
sort_shortest_first | feature:discover · strings.xml | Shortest first |  | Sort | Option | Missing
sort_newest | feature:discover · strings.xml | Newest |  | Sort | Option | Missing
detail_lesson_title | feature:discover · strings.xml | A little lesson |  | Lesson panel | Heading | Missing
detail_narrated_story | feature:discover · strings.xml | Narrated story |  | Narration row | Heading | Missing
detail_narration_desc | feature:discover · strings.xml | Warm, expressive voice · %1$s |  | Narration row | %1$s = language | Missing
detail_listen | feature:discover · strings.xml | Listen to Story |  | Sticky CTA | Button | Missing
detail_read | feature:discover · strings.xml | Read Story |  | Sticky CTA | Button | Missing
create_title | feature:create · strings.xml | Create a Story |  | Top bar | Title | Missing
create_parent_guided | feature:create · strings.xml | Parent guided |  | Top bar label | Short | Missing
create_intro_title | feature:create · strings.xml | Let’s turn today into a story. |  | Intro | Title | Missing
create_intro_body | feature:create · strings.xml | Tell us about your child’s day. We’ll turn the little moments into a magical adventure. |  | Intro | Body | Missing
create_what_happened | feature:create · strings.xml | What happened today? |  | Textarea label | Label | Missing
create_placeholder | feature:create · strings.xml | %1$s helped a friend at school and played cricket in the evening… |  | Textarea placeholder | Neutral wording proposed (design: 'his friend') | Missing
create_counter | feature:create · strings.xml | %1$d/%2$d |  | Counter | Format | Missing
create_suggest_school | feature:create · strings.xml | A day at school |  | Suggestion chip | Chip | Missing
create_suggest_family | feature:create · strings.xml | A family adventure |  | Suggestion chip | Chip | Missing
create_suggest_funny | feature:create · strings.xml | Something funny happened |  | Suggestion chip | Chip | Missing
create_suggest_learned | feature:create · strings.xml | I learned something new |  | Suggestion chip | Chip | Missing
create_suggest_kindness | feature:create · strings.xml | An act of kindness |  | Suggestion chip | Chip | Missing
create_story_hero | feature:create · strings.xml | Story hero |  | Hero selector (uppercased) | Label | Missing
create_hero_value | feature:create · strings.xml | %1$s, %2$d years |  | Hero selector | Plural/format | Missing
create_select_child_cd | feature:create · strings.xml | Select child |  | Hero select | A11y | Missing
create_story_theme | feature:create · strings.xml | Story theme |  | Field label | Label | Missing
create_more_options | feature:create · strings.xml | More options |  | Collapsible | Short | Missing
create_mood | feature:create · strings.xml | Mood |  | Field label | Label | Missing
mood_calm | feature:create · strings.xml | Calm |  | Mood chip | Chip | Missing
mood_funny | feature:create · strings.xml | Funny |  | Mood chip | Chip | Missing
mood_magical | feature:create · strings.xml | Magical |  | Mood chip | Chip | Missing
mood_adventurous | feature:create · strings.xml | Adventurous |  | Mood chip | Chip | Missing
create_duration | feature:create · strings.xml | Duration |  | Field label | Label | Missing
duration_minutes_long | core:ui · strings.xml | %1$d minutes |  | Duration chip / sleep timer | Plural | Missing
create_story_language | feature:create · strings.xml | Story language |  | Field label | Label | Missing
create_safety_title | feature:create · strings.xml | Made safely, just for your family |  | Safety note | Bold line | Missing
create_safety_body | feature:create · strings.xml | Your story details stay private and are never shared publicly. |  | Safety note | Body | Missing
create_submit | feature:create · strings.xml | Create My Story |  | Primary CTA (✦ is decorative) | Button | Missing
create_error_empty | feature:create · strings.xml | Tell us one little moment to begin the story. |  | Validation banner | Error | Missing
gen_eyebrow | feature:create · strings.xml | A story for %1$s |  | Generating (uppercased) | Format | Missing
gen_title | feature:create · strings.xml | Creating your little adventure… |  | Generating | Title | Missing
gen_body | feature:create · strings.xml | We’re weaving today’s moments into something wonderful. |  | Generating | Body | Missing
gen_progress_percent | feature:create · strings.xml | %1$d%% |  | Progress | Format | Missing
gen_stage_imagining | feature:create · strings.xml | Imagining the adventure |  | Stage 1 | Single line | Missing
gen_stage_writing | feature:create · strings.xml | Writing the story |  | Stage 2 | Single line | Missing
gen_stage_narration | feature:create · strings.xml | Preparing the narration |  | Stage 3 | Single line | Missing
gen_footnote | feature:create · strings.xml | This usually takes less than a minute. |  | Generating | Small | Missing
gen_cancel_cd | feature:create · strings.xml | Stop creating the story |  | Close button | A11y | Missing
gen_paused_title | feature:create · strings.xml | Story creation paused |  | Paused state | Title | Missing
gen_paused_body | feature:create · strings.xml | Your idea is still here. Continue whenever you’re ready. |  | Paused state | Body | Missing
gen_back_to_idea | feature:create · strings.xml | Back to your idea |  | Paused state | Button | Missing
ready_ribbon | feature:create · strings.xml | Your story is ready |  | Success ribbon | Single line | Missing
ready_made_for | feature:create · strings.xml | Made for %1$s |  | Cover badge | Format | Missing
ready_eyebrow | feature:create · strings.xml | A magical adventure |  | Eyebrow (uppercased) | Single line | Missing
ready_peek_title | feature:create · strings.xml | A little peek inside |  | Pull quote | Label | Missing
ready_listen_now | feature:create · strings.xml | Listen Now |  | CTA | Button | Missing
ready_saved_title | feature:create · strings.xml | Saved to My Stories |  | Row | Bold | Missing
ready_saved_body | feature:create · strings.xml | Find it anytime in Created by Me |  | Row | Small | Missing
reader_title | feature:reader · strings.xml | Reading |  | Top bar | Title | Missing
reader_page_of | feature:reader · strings.xml | %1$d of %2$d |  | Page indicator | Format | Missing
reader_text_smaller_cd | feature:reader · strings.xml | Decrease text size |  | A− button | A11y | Missing
reader_text_larger_cd | feature:reader · strings.xml | Increase text size |  | A+ button | A11y | Missing
reader_previous | feature:reader · strings.xml | Previous |  | Bottom bar | Button | Missing
reader_next | feature:reader · strings.xml | Next |  | Bottom bar | Button | Missing
reader_play_narration_cd | feature:reader · strings.xml | Play narration |  | Play button | A11y | Missing
player_story_text | feature:reader · strings.xml | Story text |  | Top link | Short | Missing
player_now_playing_for | feature:reader · strings.xml | Now playing for %1$s |  | Label (uppercased) | Format | Missing
player_language_narrator | feature:reader · strings.xml | %1$s · Narrated by %2$s |  | Subtitle | Format | Missing
player_simulated_note | feature:reader · strings.xml | Sample narration (preview) |  | Simulation label – NEW, not in design | Short; wording TBD | Missing
player_play_cd | feature:reader · strings.xml | Play |  | Main button | A11y | Missing
player_pause_cd | feature:reader · strings.xml | Pause |  | Main button | A11y | Missing
player_rewind_cd | feature:reader · strings.xml | Rewind 15 seconds |  | Control | A11y | Missing
player_forward_cd | feature:reader · strings.xml | Forward 15 seconds |  | Control | A11y | Missing
player_prev_chapter_cd | feature:reader · strings.xml | Previous chapter |  | Control | A11y | Missing
player_next_chapter_cd | feature:reader · strings.xml | Next chapter |  | Control | A11y | Missing
player_progress_cd | feature:reader · strings.xml | Playback progress |  | Slider | A11y | Missing
player_volume_cd | feature:reader · strings.xml | Volume |  | Slider | A11y | Missing
player_sleep_timer | feature:reader · strings.xml | Sleep timer |  | Secondary control / sheet title | Short | Missing
player_speed | feature:reader · strings.xml | Speed |  | Secondary control | Short | Missing
player_speed_value | feature:reader · strings.xml | %1$s× |  | Speed value | Format | Missing
sleep_timer_body | feature:reader · strings.xml | Audio will gently stop when the timer ends. |  | Sheet | Body | Missing
sleep_timer_end_of_story | feature:reader · strings.xml | End of story |  | Sheet option | Option | Missing
library_title | feature:library · strings.xml | My Stories |  | Top bar | Title | Missing
library_search_hint | feature:library · strings.xml | Search your stories |  | Search | Single line | Missing
library_tab_all | feature:library · strings.xml | All |  | Tab | Tab | Missing
library_tab_created | feature:library · strings.xml | Created by Me |  | Tab | Tab – may scroll | Missing
library_tab_downloaded | feature:library · strings.xml | Downloaded |  | Tab | Tab | Missing
library_tab_favourites | feature:library · strings.xml | Favourites |  | Tab | Tab | Missing
library_recently_played | feature:library · strings.xml | Recently played |  | Section | Heading | Missing
library_remaining | feature:library · strings.xml | %1$s remaining |  | Recently played | Format | Missing
library_collection | feature:library · strings.xml | Your collection |  | Section | Heading | Missing
library_meta | feature:library · strings.xml | %1$d min · %2$s years |  | Row meta | Format | Missing
library_empty_downloaded_title | feature:library · strings.xml | Ready for offline adventures? |  | Empty state | Heading | Missing
library_empty_downloaded_body | feature:library · strings.xml | Download a story and bedtime can travel anywhere. |  | Empty state | Body | Missing
library_empty_title | feature:library · strings.xml | No stories here yet |  | Empty state | Heading | Missing
library_empty_body | feature:library · strings.xml | Tap the heart on a story you love to keep it close. |  | Empty state | Body | Missing
library_discover_stories | feature:library · strings.xml | Discover stories |  | Empty CTA | Button | Missing
library_manage_downloads_cd | feature:library · strings.xml | Manage downloads |  | Top bar icon | A11y | Missing
library_play_story_cd | feature:library · strings.xml | Play story |  | Row button | A11y | Missing
settings_title | feature:settings · strings.xml | Profile |  | Top bar | Title | Missing
settings_account | feature:settings · strings.xml | Account settings |  | Parent card | Link | Missing
settings_group_children | feature:settings · strings.xml | Children |  | Group (uppercased) | Heading | Missing
settings_manage_children | feature:settings · strings.xml | Manage children |  | Row | Title | Missing
settings_children_summary | feature:settings · strings.xml | %1$s and %2$s |  | Row subtitle | Format (list formatting for >2) | Missing
settings_language_prefs | feature:settings · strings.xml | Language preferences |  | Row | Title | Missing
settings_group_experience | feature:settings · strings.xml | Experience |  | Group (uppercased) | Heading | Missing
settings_bedtime_reminders | feature:settings · strings.xml | Bedtime reminders |  | Row | Title | Missing
settings_every_day_at | feature:settings · strings.xml | Every day at %1$s |  | Row subtitle | Locale time | Missing
settings_notifications | feature:settings · strings.xml | Notifications |  | Row | Title | Missing
settings_notifications_sub | feature:settings · strings.xml | Stories and family updates |  | Row subtitle | Small | Missing
settings_audio_prefs | feature:settings · strings.xml | Audio preferences |  | Row | Title | Missing
settings_audio_sub | feature:settings · strings.xml | %1$s · %2$s speed |  | Row subtitle | Format | Missing
settings_normal_speed | feature:settings · strings.xml | Normal |  | Speed name | Short | Missing
settings_download_settings | feature:settings · strings.xml | Download settings |  | Row | Title | Missing
settings_wifi_only | feature:settings · strings.xml | Wi-Fi only |  | Row subtitle | Small | Missing
settings_group_app | feature:settings · strings.xml | LittleStory |  | Group (uppercased) | Brand | Missing
settings_subscription | feature:settings · strings.xml | Subscription |  | Row | Title | Missing
settings_free_plan | feature:settings · strings.xml | Free plan |  | Row subtitle | Small | Missing
settings_privacy | feature:settings · strings.xml | Privacy & parent controls |  | Row | Title | Missing
settings_privacy_sub | feature:settings · strings.xml | Your family’s data and safety |  | Row subtitle | Small | Missing
settings_help | feature:settings · strings.xml | Help & about |  | Row | Title | Missing
settings_version | feature:settings · strings.xml | Version %1$s |  | Row subtitle | Format | Missing
settings_footer | feature:settings · strings.xml | Stories created with care. Profiles are private and parent-managed. |  | Footer | Body | Missing
profiles_title | feature:settings · strings.xml | Child Profiles |  | Top bar | Title | Missing
profiles_add_child | feature:settings · strings.xml | Add child |  | Top bar action | Short | Missing
profiles_privacy_title | feature:settings · strings.xml | Private family profiles |  | Note | Bold | Missing
profiles_privacy_body | feature:settings · strings.xml | Only you can see and manage your children’s details. |  | Note | Body | Missing
profiles_age_language | feature:settings · strings.xml | %1$d years · %2$s |  | Card | Plural/format | Missing
profiles_active | feature:settings · strings.xml | Active |  | Pill | Short | Missing
profiles_switch | feature:settings · strings.xml | Switch |  | Pill | Short | Missing
profiles_edit_cd | feature:settings · strings.xml | Edit %1$s’s profile |  | Pencil | A11y | Missing
profiles_add_another_title | feature:settings · strings.xml | Add another child |  | Dashed row | Bold | Missing
profiles_add_another_body | feature:settings · strings.xml | Personalise stories for every little listener |  | Dashed row | Small | Missing
sub_eyebrow | feature:settings · strings.xml | LittleStory Premium |  | Hero (uppercased) | Single line | Missing
sub_title | feature:settings · strings.xml | Make every bedtime magical. |  | Hero | Title | Missing
sub_body | feature:settings · strings.xml | More wonder, more listening, and stories that grow with your family. |  | Hero | Body | Missing
sub_benefit_personalised | feature:settings · strings.xml | More personalised stories |  | Benefit | Short | Missing
sub_benefit_collections | feature:settings · strings.xml | Premium story collections |  | Benefit | Short | Missing
sub_benefit_audio | feature:settings · strings.xml | Audio narration |  | Benefit | Short | Missing
sub_benefit_offline | feature:settings · strings.xml | Offline downloads |  | Benefit | Short | Missing
sub_benefit_profiles | feature:settings · strings.xml | Multiple child profiles |  | Benefit | Short | Missing
sub_benefit_weekly | feature:settings · strings.xml | New stories every week |  | Benefit | Short | Missing
sub_plan_free | feature:settings · strings.xml | Free |  | Plan | Short | Missing
sub_plan_premium | feature:settings · strings.xml | Premium %1$s |  | Plan name | Format | Missing
sub_plan_monthly | feature:settings · strings.xml | Monthly |  | Plan | Short | Missing
sub_plan_yearly | feature:settings · strings.xml | Yearly |  | Plan | Short | Missing
sub_plan_family | feature:settings · strings.xml | Family |  | Plan | Short | Missing
sub_note_free | feature:settings · strings.xml | Try the magic |  | Plan note | Small | Missing
sub_note_month | feature:settings · strings.xml | per month |  | Plan note | Small | Missing
sub_note_year_best | feature:settings · strings.xml | per year · best value |  | Plan note | Small | Missing
sub_note_family | feature:settings · strings.xml | per year · up to %1$d children |  | Plan note | Plural | Missing
sub_best_value | feature:settings · strings.xml | Best value |  | Tag (uppercased) | Very short | Missing
sub_disclaimer | feature:settings · strings.xml | Illustrative pricing only. No real payment will be processed. |  | Note | Small | Missing
sub_choose_plan | feature:settings · strings.xml | Choose %1$s Plan |  | CTA | Button | Missing
sub_restore | feature:settings · strings.xml | Restore purchases |  | Link | Small | Missing
sub_terms | feature:settings · strings.xml | Terms |  | Link | Small | Missing
sub_privacy | feature:settings · strings.xml | Privacy |  | Link | Small | Missing
sub_dialog_title | feature:settings · strings.xml | Plan selected |  | Dialog | Title | Missing
sub_dialog_body | feature:settings · strings.xml | This is a prototype, so no payment was made. You selected the %1$s plan. |  | Dialog | Body | Missing
reminder_title | feature:settings · strings.xml | Bedtime Reminder |  | Top bar | Title | Missing
reminder_visual_title | feature:settings · strings.xml | A gentle nudge for storytime |  | Panel | Title | Missing
reminder_visual_body | feature:settings · strings.xml | We’ll keep it quiet and calm—just one reminder. |  | Panel | Body | Missing
reminder_toggle | feature:settings · strings.xml | Bedtime reminder |  | Toggle row | Bold | Missing
reminder_pause_anytime | feature:settings · strings.xml | Pause anytime |  | Toggle row | Small | Missing
reminder_time | feature:settings · strings.xml | Reminder time |  | Field | Label | Missing
reminder_repeat_on | feature:settings · strings.xml | Repeat on |  | Field | Label | Missing
reminder_quiet_title | feature:settings · strings.xml | Quiet bedtime experience |  | Quiet row | Bold | Missing
reminder_quiet_body | feature:settings · strings.xml | No sound, no bright alerts |  | Quiet row | Small | Missing
reminder_save | feature:settings · strings.xml | Save reminder |  | CTA | Button | Missing
reminder_saved_toast | feature:settings · strings.xml | Reminder saved for %1$s |  | Toast | Locale time | Missing
reminder_day_initials | feature:settings · strings.xml | (use DayOfWeek TextStyle.NARROW) |  | Day buttons | Not a string resource – locale API | Missing
downloads_title | feature:library · strings.xml | Offline Downloads |  | Top bar | Title | Missing
downloads_used | feature:library · strings.xml | %1$d MB used |  | Storage card | Format | Missing
downloads_of_available | feature:library · strings.xml | of %1$s available for stories |  | Storage card | Format | Missing
downloads_size_meta | feature:library · strings.xml | %1$d MB · Audio & story |  | Row | Format | Missing
downloads_remove_cd | feature:library · strings.xml | Remove download of %1$s |  | ✕ | A11y | Missing
downloads_empty_title | feature:library · strings.xml | No downloads yet |  | Empty state | Heading | Missing
downloads_empty_body | feature:library · strings.xml | Save a few favourites for journeys, power cuts, and cosy nights away. |  | Empty state | Body | Missing
downloads_find_story | feature:library · strings.xml | Find a story |  | Empty CTA | Button | Missing
downloads_tip_title | feature:library · strings.xml | Offline means worry-free |  | Tip | Bold | Missing
downloads_tip_body | feature:library · strings.xml | Downloaded stories work without internet and stay private on this device. |  | Tip | Body | Missing
notifications_title | feature:settings · strings.xml | Notifications |  | Top bar | Title | Missing
notifications_mark_all_read | feature:settings · strings.xml | Mark all read |  | Top bar action | Short | Missing
notifications_today | feature:settings · strings.xml | Today |  | Section (uppercased) | Heading | Missing
notifications_earlier | feature:settings · strings.xml | Earlier |  | Section (uppercased) | Heading | Missing
notifications_unread_cd | feature:settings · strings.xml | Unread |  | Unread dot | A11y | Missing
story_1.title | assets/mock/stories_kn.json | The Little Elephant Who Shared |  | Story title | Content | Missing |  | Mock content – not strings.xml
story_1.synopsis | assets/mock/stories_kn.json | A gentle adventure about friendship, generosity, and discovering that sharing can make everyone happier. |  | Detail | Content | Missing |  | Mock content – not strings.xml
story_1.lesson | assets/mock/stories_kn.json | Sharing, generosity and caring for friends. |  | Detail lesson | Content | Missing |  | Mock content – not strings.xml
story_1.featured_blurb | assets/mock/stories_kn.json | A tender tale about kindness and a basket of mangoes. |  | Discover featured | Content | Missing |  | Mock content – not strings.xml
story_2.title | assets/mock/stories_kn.json | Aarav and the Magical Cricket Bat |  | Story title | Content | Missing |  | Mock content – not strings.xml
story_2.synopsis | assets/mock/stories_kn.json | A kind choice leads Aarav onto a moonlit cricket pitch, where helping a new friend creates the brightest magic of all. |  | Story Ready | Content | Missing |  | Mock content – not strings.xml
story_2.pages[0..4] | assets/mock/stories_kn.json | 5 paragraphs (see prototype storyParagraphs) |  | Reader | Content – long | Missing |  | Mock content – not strings.xml
story_3.title | assets/mock/stories_kn.json | Mira and the Moonlit Garden |  | Story title | Content | Missing |  | Mock content – not strings.xml
story_4.title | assets/mock/stories_kn.json | The Banyan Tree’s Secret |  | Story title | Content | Missing |  | Mock content – not strings.xml
story_5.title | assets/mock/stories_kn.json | Ananya’s Journey to the Stars |  | Story title | Content | Missing |  | Mock content – not strings.xml
story_6.title | assets/mock/stories_kn.json | The Lanterns of Jaipur |  | Story title | Content | Missing |  | Mock content – not strings.xml
notif_1.title / body | assets/mock/notifications_kn.json | Your new story is ready / Aarav and the Magical Cricket Bat is waiting for bedtime. |  | Notifications | Content | Missing |  | Mock content – not strings.xml
notif_2.title / body | assets/mock/notifications_kn.json | Storytime is at 8:30 PM / Slow down together with a calm bedtime favourite. |  | Notifications | Content | Missing |  | Mock content – not strings.xml
notif_3.title / body | assets/mock/notifications_kn.json | Fresh tales from India / Three new stories about friendship, family and wonder. |  | Notifications | Content | Missing |  | Mock content – not strings.xml
Note on D1: Fill Kannada here. Keep status 'Needs native review' until a fluent reviewer approves.

## Prompt Library
Prompt File | Path in Repo | Purpose | Phase | Used By | Status
00_MASTER_ORCHESTRATOR_PROMPT.md | prompts/00_MASTER_ORCHESTRATOR_PROMPT.md | Master orchestration | All | Governs every other prompt | To create (LS-006)
01_REPOSITORY_DISCOVERY_PROMPT.md | prompts/01_REPOSITORY_DISCOVERY_PROMPT.md | Repository discovery | P0 | LS-001 | To create (LS-006)
02_FIGMA_AUDIT_PROMPT.md | prompts/02_FIGMA_AUDIT_PROMPT.md | Figma / design-pack audit | P0 | LS-002 | To create (LS-006)
03_REQUIREMENTS_AND_EDGE_CASES_PROMPT.md | prompts/03_REQUIREMENTS_AND_EDGE_CASES_PROMPT.md | Requirements analysis | P1 | LS-003 | To create (LS-006)
04_ARCHITECTURE_DESIGN_PROMPT.md | prompts/04_ARCHITECTURE_DESIGN_PROMPT.md | Architecture design & ADRs | P1 | LS-008 | To create (LS-006)
05_JIRA_BACKLOG_GENERATION_PROMPT.md | prompts/05_JIRA_BACKLOG_GENERATION_PROMPT.md | Backlog generation / update | P1 | This workbook | To create (LS-006)
06_PHASE_EXECUTION_PROMPT.md | prompts/06_PHASE_EXECUTION_PROMPT.md | Phase execution | P2–P8 | Phase kick-off | To create (LS-006)
07_TICKET_IMPLEMENTATION_TEMPLATE.md | prompts/07_TICKET_IMPLEMENTATION_TEMPLATE.md | Ticket implementation | P2–P8 | Every ticket | To create (LS-006)
08_COMPOSE_UI_IMPLEMENTATION_PROMPT.md | prompts/08_COMPOSE_UI_IMPLEMENTATION_PROMPT.md | Compose UI implementation | P2–P6 | UI tickets | To create (LS-006)
09_VISUAL_REGRESSION_PROMPT.md | prompts/09_VISUAL_REGRESSION_PROMPT.md | Visual regression | P7 | LS-122, LS-124 | To create (LS-006)
10_INTEGRATION_TESTING_PROMPT.md | prompts/10_INTEGRATION_TESTING_PROMPT.md | Integration testing | P7 | LS-121 | To create (LS-006)
11_ACCESSIBILITY_REVIEW_PROMPT.md | prompts/11_ACCESSIBILITY_REVIEW_PROMPT.md | Accessibility review | P7 | LS-123 | To create (LS-006)
12_SECURITY_REVIEW_PROMPT.md | prompts/12_SECURITY_REVIEW_PROMPT.md | Security review | P7 | LS-126 | To create (LS-006)
13_CODE_REVIEW_PROMPT.md | prompts/13_CODE_REVIEW_PROMPT.md | PR / code review | All | Every PR | To create (LS-006)
14_CI_DIAGNOSTICS_PROMPT.md | prompts/14_CI_DIAGNOSTICS_PROMPT.md | CI repair | All | CI failures | To create (LS-006)
15_PR_PREPARATION_PROMPT.md | prompts/15_PR_PREPARATION_PROMPT.md | PR preparation | All | Every PR | To create (LS-006)
16_POST_MERGE_VERIFICATION_PROMPT.md | prompts/16_POST_MERGE_VERIFICATION_PROMPT.md | Post-merge verification | All | After each merge | To create (LS-006)
17_RELEASE_READINESS_PROMPT.md | prompts/17_RELEASE_READINESS_PROMPT.md | Release readiness | P8 | LS-133 | To create (LS-006)
18_BACKEND_INTEGRATION_PLANNING_PROMPT.md | prompts/18_BACKEND_INTEGRATION_PLANNING_PROMPT.md | Backend planning | P8 | LS-140, LS-141 | To create (LS-006)
19_LOCALIZATION_REVIEW_PROMPT.md | prompts/19_LOCALIZATION_REVIEW_PROMPT.md | Localization review | P6–P7 | LS-043, LS-047 | To create (LS-006)
20_ADD_NEW_LANGUAGE_PROMPT.md | prompts/20_ADD_NEW_LANGUAGE_PROMPT.md | Add a new language | Future | LS-048 | To create (LS-006)
21_MAINTAINABILITY_AND_HARDCODING_REVIEW_PROMPT.md | prompts/21_MAINTAINABILITY_AND_HARDCODING_REVIEW_PROMPT.md | Maintainability / hardcoding review | P7 | LS-125 | To create (LS-006)
LS-###.md (one per ticket) | prompts/tickets/LS-###.md | Per-ticket implementation prompt | P2–P8 | Every ticket | To create (LS-006)
Master orchestrator (this project) | LittleStory_Master_Orchestrator_Prompt.md | Source of truth for all prompts | All | Orchestrator | Exists – copy to prompts/00_…

## Lists (hidden)
Status | Priority | MoSCoW | Phase | Type | Parallel | Conflict | L10n | KN | Result | Check | Risk | DesignStatus | ImplStatus
To Do | Highest | Must | P0 | Epic | Yes | Low | None | N/A | Not run | Not started | Low | Design Ready | Not started
In Progress | High | Should | P1 | Story | No | Medium | New strings | Missing | Pass | Pending | Medium | Design Ready (spec only) | In progress
In Review | Medium | Could | P2 | Task | After deps | High | Content | Draft | Fail | Pass | High | Design Missing | Implemented
Blocked | Low | Won't | P3 | Bug |  |  | Layout risk | Needs native review | Blocked | Fail |  | Needs Figma Verification | Verified
Done |  |  | P4 | Spike |  |  |  | Approved |  | N/A
Needs Clarification |  |  | P5
P6
P7
P8